## Dashboard Monthly
Other Task List |  | Overdue List
TASK | Qty | WW | Type | TASK | PRODUCT | Target Date
Training | 20
Visit Exhibition | 5
Create standard document | 2
5S meeting | 2
Interview candidate new member | 1
Support register document | 1
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
On time :
Delay :
100.0%
0.0%
Completed Task :
659

## Dashboard Weekly
้
t
Other Task List |  | Overdue List
TASK | Qty | WW | Type | TASK | PRODUCT | Target Date
Training | 20
Visit Exhibition | 5
Create standard document | 2
5S meeting | 2
Interview candidate new member | 1
Support register document | 1
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
On time :
Delay :
100.0%
0.0%
Completed Task :
659

## Schedule2026
NPI INTEGRATION FRONTED TASK SCHEDULE | [6 empty] | 2026-07-10 |  |  | Week 28 |  |  |  | 2026-01-01
[5 empty] | % Type | % Closed | [7 empty] | 2026-06-29
|  |  |  | DFM Mold | 9.61% | 100% | [7 empty] | Start Gantt Week: | [5 empty] | 27
|  |  |  | OTHER | 4.655% | 100%
|  |  |  | NPI | 28.08% | 99.47% | [7 empty] | Edit the week number to update the display
|  |  |  | Part DFM | 2.252% | 100%
|  |  |  | MEETING | 11.26% | 100% | [6 empty] | July | [6 empty] | July | [6 empty] | July | [6 empty] | July
|  |  |  | RFQ | 10.06% | 97.01% | [6 empty] | WW 27 | [6 empty] | WW 28 | [6 empty] | WW 29 | [6 empty] | WW 30
|  |  |  | PROJECT | 1.051% | 85.71% | [6 empty] | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26
|  |  |  | Packing | 29.88% | [7 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
WW | Month | Type | TASK | PRODUCT/Description | CUSTOMER | PIC | Start Date | Target Date | Finish Date | Status | OverDue Aleart | Performace status | Column1 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column110 | Column111 | Column112 | Column113 | Column114 | Column115 | Column116 | Column117 | Column118 | Column119 | Column120 | Column121 | Column122 | Column123 | Column124 | Column125 | Column126 | Column127 | Column128
2 | Jan | NPI | NPI Technical support | AMW 03457 Follow up customer comment about dimension outspec or not of part screen protection | Numworks | Thiti | 2026-01-05 | 2026-01-05 | 2026-01-05 | Close | Closed | On Time
2 | Jan | NPI | NPI Technical support | Confirm drawing to SRC about area texture on logo of part BOX of JRI model | JRI | thiti | 2026-01-06 | 2026-01-06 | 2026-01-06 | Close | Closed | On Time
2 | Jan | NPI | NPI Technical support | Support made 2D drawing printing detial of Numworks school Property project | Numworks | Thiti | 2026-01-06 | 2026-01-07 | 2026-01-07 | Close | Closed | On Time
2 | Jan | NPI | NPI Technical support | AMW 03457 Support SRC review cost laser engraving JIG | Numworks | Thiti | 2026-01-07 | 2026-01-08 | 2026-01-08 | Close | Closed | On Time
2 | Jan | NPI | Review JIG concept | AMW 03457 Review concept jig design for attached foam screen | Numworks | Thiti | 2026-01-07 | 2026-01-07 | 2026-01-07 | Close | Closed | On Time
2 | Jan | MEETING | Meeting | AMW 03457 N0102 Numworks weekly progress | Numworks | Thiti | 2026-01-08 | 2026-01-08 | 2026-01-08 | Close | Closed | On Time
3 | Jan | NPI | NPI Technical support | Confirm handmafe sample modify idea of Jointpile | JRI | Thiti | 2026-01-12 | 2026-01-12 | 2026-01-12 | Close | Closed | On Time
3 | Jan | NPI | NPI Technical support | Study overmold concept for new JRI project | JRI | Thiti | 2026-01-12 | 2026-01-12 | 2026-01-12 | Close | Closed | On Time
3 | Jan | NPI | NPI Technical support | Visit new supplier Tontec |  | Thiti | 2026-01-13 | 2026-01-13 | 2026-01-13 | Close | Closed | On Time
3 | Jan | NPI | NPI Technical support | Review modify cost for Laser Engraving base jig JRI | JRI | Thiti | 2026-01-14 | 2026-01-14 | 2026-01-14 | Close | Closed | On Time
3 | Jan | NPI | NPI Technical support | AMW 03457 Review inspection report of NW ( 6 parts ) and judgement for using in assembly | Numworks | Thiti | 2026-01-14 | 2026-01-15 | 2026-01-15 | Close | Closed | On Time
3 | Jan | MEETING | Meeting | JRI weekly meeting | JRI | Thiti | 2026-01-14 | 2026-01-14 | 2026-01-14 | Close | Closed | On Time
3 | Jan | NPI | NPI Technical support | Confirm handmafe sample modify idea of Jointpile rev2 | JRI | Thiti | 2026-01-16 | 2026-01-16 | 2026-01-16 | Close | Closed | On Time
4 | Jan | Part DFM | Review internal DFM | AMW 03667 Review New JRI Digital Sensor mode | JRI | Thiti | 2026-01-19 | 2026-01-20 | 2026-01-20 | Close | Closed | On Time
4 | Jan | Part DFM | Review internal DFM | AMW 03668 Review New JRI Digital Sensor mode | JRI | Thiti | 2026-01-19 | 2026-01-20 | 2026-01-20 | Close | Closed | On Time
4 | Jan | Part DFM | Review internal DFM | AMW 03669 Review New JRI Digital Sensor model | JRI | Thiti | 2026-01-20 | 2026-01-21 | 2026-01-20 | Close | Closed | On Time
4 | Jan | Part DFM | Review internal DFM | AMW 036670 Review New JRI Digital Sensor model | JRI | Thiti | 2026-01-20 | 2026-01-21 | 2026-01-20 | Close | Closed | On Time
4 | Jan | NPI | Sample assembly Support | AMW 03457 Numworks final sample assembly 12 pcs. (PCBA Assy with Plastic T2) | Numworks | Thiti | 2026-01-23 | 2026-01-23 | 2026-01-23 | Close | Closed | On Time
4 | Jan | NPI | NPI Technical support | JRI Prepare modification report of JRI-Trapp | JRI | Thiti | 2026-01-23 | 2026-01-23 | 2026-01-23 | Close | Closed | On Time
5 | Jan | MEETING | Meeting | JRI Weekly progress | JRI | Thiti | 2026-01-26 | 2026-01-26 | 2026-01-26 | Close | Closed | On Time
5 | Jan | NPI | NPI Technical support | JRI GDS Review update drawing from customer and R&D | JRI | Thiti | 2026-01-26 | 2026-01-27 | 2026-01-27 | Close | Closed | On Time
5 | Jan | DFM Mold | Review DFM Part Drawing and feed back | AMW 03577 Review DFM part | FONROCHE | Thiti | 2026-01-27 | 2026-01-28 | 2026-01-28 | Close | Closed | On Time
5 | Jan | NPI | NPI Technical support | AMW 03211 Rubber Button no click, Follow measurement shore result and solution to increase shore | Enersys | Thiti | 2026-01-27 | 2026-01-29 | 2026-01-29 | Close | Closed | On Time
5 | Jan | NPI | NPI Technical support | AMW 03210,03211 Support eng. trial part ring for fine solution to improve ring not lock. | Enersys | Thiti | 2026-01-28 | 2026-01-28 | 2026-01-28 | Close | Closed | On Time
5 | Jan | NPI | NPI Technical support | JRI waiting customer confirm modification report of JRI-Trapp |  | Thiti | 2026-01-29 | 2026-01-29 | 2026-01-29 | Close | Closed | On Time
5 | Jan | MEETING | Meeting | Numworks weekly meeting | Numworks | Thiti | 2026-01-29 | 2026-01-29 | 2026-01-29 | Close | Closed | On Time
5 | Jan | DFM Mold | Review DFM MOLD and feed back | AMW 03577 DFM mold meeting | FONROCHE | Thiti | 2026-01-29 | 2026-01-29 | 2026-01-29 | Close | Closed | On Time
5 | Jan | NPI | NPI Technical support | JRI Request supplier addition sheet protect for ultrasonic weldding, follow up result. | JRI | Thiti | 2026-01-30 | 2026-01-30 | 2026-01-30 | Close | Closed | On Time
6 | Feb | NPI | NPI Technical support | Go to supplier to discuss idea improve foam screen packing standard for MP | Numworks | Thiti | 2026-02-02 | 2026-02-02 | 2026-02-02 | Close | Closed | On Time
6 | Feb | NPI | NPI Technical support | JRI, Support SRC review modify cost of trape | JRI | Thiti | 2026-02-03 | 2026-02-03 | 2026-02-03 | Close | Closed | On Time
6 | Feb | OTHER | Create standard document | Make New part control sheet document for viper 6 bay | Enersys | Thiti | 2026-02-04 | 2026-02-04 | 2026-02-04 | Close | Closed | On Time
6 | Feb | MEETING | Meeting | Numworks pilot build plan meeting | Numworks | Thiti | 2026-02-04 | 2026-02-04 | 2026-02-04 | Close | Closed | On Time
6 | Feb | NPI | NPI Technical support | JRI, Clear concept modify trappe | JRI | Thiti | 2026-02-06 | 2026-02-06 | 2026-02-06 | Close | Closed | On Time
7 | Feb | OTHER | Training | Training Solidworks: Assembly modeling |  | Thiti | 2026-02-09 | 2026-02-11 | 2026-02-11 | Close | Closed | On Time
7 | Feb | NPI | NPI Technical support | AMW 03457 confirm foam screen new sample | Numworks | Thiti | 2026-02-12 | 2026-02-12 | 2026-02-12 | Close | Closed | On Time
7 | Feb | NPI | NPI Technical support | AMW 03210,03211 Trial Main door improve gap problem | Enersys | Thiti | 2026-02-12 | 2026-02-12 | 2026-02-12 | Close | Closed | On Time
7 | Feb | MEETING | Meeting | Numworks weekly meeting | Numworks | Thiti | 2026-02-12 | 2026-02-12 | 2026-02-12 | Close | Closed | On Time
9 | Feb | PACKING | Design New Packaging | Request SCN update part packing in process_IES 50kw | IES | Kamonchanok | 2026-02-25 | 2026-02-25 | 2026-02-25 | Close | Closed | On Time
8 | Feb | OTHER | Training | Training Solidworks: Surface modeling |  | Thiti | 2026-02-16 | 2026-02-17 | 2026-02-17 | Close | Closed | On Time
10 | Mar | OTHER | Training | Training Solidworks: Drawing |  | Thiti | 2026-03-04 | 2026-03-05 | 2026-03-05 | Close | Closed | On Time
2 | Jan | NPI | Pilot assembly Support | AMW QUO866 _project 4020 SIREM | Enersys | Kamonchanok | 2026-01-07 | 2026-01-08 | 2025-12-26 | Close | Closed | On Time
2 | Jan | PACKING | Support packing | AMW 03314 Support customer audit: Packing part | LEACH | Kamonchanok | 2026-01-07 | 2026-01-07 | 2026-01-07 | Close | Closed | On Time
2 | Jan | RFQ | RFQ Packing | AMW-QUO874 RFQ Packing | JRI | Kamonchanok | 2026-01-08 | 2026-01-09 | 2026-01-08 | Close | Closed | On Time
2 | Jan | PACKING | Support packing | AMW 03513 Support packing >> 4 Pcs | IES | Kamonchanok | 2026-01-08 | 2026-01-08 | 2026-01-08 | Close | Closed | On Time
2 | Jan | PACKING | Support packing | AMW 03512 Support packing >> 2 Pcs | IES | Kamonchanok | 2026-01-08 | 2026-01-08 | 2026-01-08 | Close | Closed | On Time
2 | Jan | PACKING | Design New Packaging | Request supplier join AMW to improve Cabinet box new design with actual cabinet | Enersys | Kamonchanok | 2026-01-08 | 2026-01-08 | 2026-01-08 | Close | Closed | On Time
2 | Jan | PACKING | Support packing | AMW 03189 Support customer audit: Packing part | LEACH | Kamonchanok | 2026-01-08 | 2026-01-08 | 2026-01-08 | Close | Closed | On Time
3 | Jan | OTHER | Training | Training Solidworks: Essentials |  | Kamonchanok | 2026-01-12 | 2026-01-15 | 2026-01-15 | Close | Closed | On Time
3 | Jan | RFQ | RFQ Packing | AMW QUO878 RFQ Pacaking (PCBA) | Says electric | Kamonchanok | 2026-01-14 | 2026-01-15 | 2026-01-14 | Close | Closed | On Time
3 | Jan | PACKING | Support packing | Support MP BESS packing process 1 pcs | Enersys | Kamonchanok | 2026-01-16 | 2026-01-16 | 2026-01-16 | Close | Closed | On Time
3 | Jan | RFQ | RFQ Packing | AMW QUO818 Rev 3 Packaging RFQ | Gutor | Kamonchanok | 2026-01-16 | 2026-01-16 | 2026-01-16 | Close | Closed | On Time
3 | Jan | PACKING | Support packing | AMW 03211 support packing pre series show current concept to Director of development division | Enersys | Kamonchanok | 2026-01-16 | 2026-01-16 | 2026-01-16 | Close | Closed | On Time
3 | Jan | PACKING | Support packing | AMW 03211 Support Packing PanelUnit send to Customer |  | Kamonchanok | 2026-01-16 | 2026-01-16 | 2026-01-16 | Close | Closed | On Time
4 | Jan | PACKING | Design New Packaging | AMW 03501 Packaging design | Maatel | Kamonchanok | 2026-01-19 | 2026-01-20 | 2026-01-19 | Close | Closed | On Time
4 | Jan | PACKING | Design New Packaging | AMW 03502 Packaging design | Maatel | Kamonchanok | 2026-01-19 | 2026-01-20 | 2026-01-19 | Close | Closed | On Time
4 | Jan | PACKING | Design New Packaging | AMW 03503 Packaging design | Maatel | Kamonchanok | 2026-01-19 | 2026-01-20 | 2026-01-19 | Close | Closed | On Time
4 | Jan | PACKING | Design New Packaging | AMW 03396 Packaging design | Maatel | Kamonchanok | 2026-01-19 | 2026-01-20 | 2026-01-19 | Close | Closed | On Time
4 | Jan | PACKING | Design New Packaging | AMW 03210,03211 Review box for cabinet after supplier improve | Enersys | Kamonchanok | 2026-01-20 | 2026-01-20 | 2026-01-20 | Close | Closed | On Time
4 | Jan | PACKING | Support packing | AMW 03210,03211 Support packing stand to customer | Enersys | Kamonchanok | 2026-01-20 | 2026-01-20 | 2026-01-20 | Close | Closed | On Time
4 | Jan | RFQ | RFQ Packing | AMW QUO882 Viper StandAlone PCBA Packing RFQ (3 PCBA) | Enersys | Kamonchanok | 2026-01-20 | 2026-01-21 | 2026-01-21 | Close | Closed | On Time
4 | Jan | PACKING | Support packing | AMW 03210,03211 Support packing stand to customer (USA) | Enersys | Kamonchanok | 2026-01-21 | 2026-01-21 | 2026-01-21 | Close | Closed | On Time
4 | Jan | PACKING | Design New Packaging | AMW 03210,03211 Feed back to customer about Arrow printing on foam for protect Screen of Cabinet | Enersys | Kamonchanok | 2026-01-22 | 2026-01-22 | 2026-01-22 | Close | Closed | On Time
10 | Mar | OTHER | Training | Training Solidworks: Assembly modeling |  | Kamonchanok | 2026-03-04 | 2026-03-06 | 2026-03-06 | Close | Closed | On Time
4 | Jan | PACKING | Confirm packing | AMW 02715 Confirm packing part | AEG | Kamonchanok | 2026-01-23 | 2026-01-23 | 2026-01-23 | Close | Closed | On Time
5 | Jan | PACKING | Support packing | AMW 03520, 03521 support packing | FONROCHE | Kamonchanok | 2026-01-26 | 2026-01-26 | 2026-01-26 | Close | Closed | On Time
5 | Jan | PACKING | Design New Packaging | AMW 03210,03211 Review box for cabinet after supplier improve | Enersys | Kamonchanok | 2026-01-26 | 2026-01-27 | 2026-01-27 | Close | Closed | On Time
5 | Jan | RFQ | RFQ Packing | AMW QUO890 RFQ packing | Maatel | Kamonchanok | 2026-01-28 | 2026-01-29 | 2026-01-26 | Close | Closed | On Time
5 | Jan | NPI | NPI Technical support | confirm date to Fagerdala support pilot assembly shirnk wrap fix plan | Numworks | Kamonchanok | 2026-01-30 | 2026-01-30 | 2026-01-30 | Close | Closed | On Time
5 | Jan | PACKING | Support packing | AMW 03457 Numworks support packing final sample | Numworks | Kamonchanok | 2026-01-30 | 2026-01-30 | 2026-01-30 | Close | Closed | On Time
5 | Jan | PACKING | Support packing | AMW 03132 support packing 3 unit |  | Kamonchanok | 2026-01-30 | 2026-01-30 | 2026-01-30 | Close | Closed | On Time
5 | Jan | PACKING | Support packing | AMW 03275 Support packing | AEG | Kamonchanok | 2026-01-30 | 2026-01-30 | 2026-01-30 | Close | Closed | On Time
6 | Feb | RFQ | RFQ Packing | AMW QUO889 RFQ Packing | LEACH | Kamonchanok | 2026-02-02 | 2026-02-02 | 2026-01-23 | Close | Closed | On Time
6 | Feb | PACKING | Design New Packaging | Share packing concept AEG:BUSBAR 100A - Packing items of AMW 03132 & AMW 03134 | AEG | Kamonchanok | 2026-02-04 | 2026-02-04 | 2026-02-04 | Close | Closed | On Time
6 | Feb | PACKING | Support packing | AMW 03520 support packing 22 pcs | FONROCHE | Kamonchanok | 2026-02-04 | 2026-02-04 | 2026-02-04 | Close | Closed | On Time
6 | Feb | PACKING | Support packing | AMW 03521 support packing 14 pcs | FONROCHE | Kamonchanok | 2026-02-04 | 2026-02-04 | 2026-02-04 | Close | Closed | On Time
6 | Feb | PACKING | Support packing | PCBA PFC MIP 3kW support packing |  | Kamonchanok | 2026-02-06 | 2026-02-06 | 2026-02-06 | Close | Closed | On Time
6 | Feb | RFQ | RFQ Packing | AMW QUO902 RFQ packing | Statron | Kamonchanok | 2026-02-06 | 2026-02-06 | 2026-02-04 | Close | Closed | On Time
6 | Feb | PACKING | Support packing | AMW 03286-B7.1 support packing | Enersys | Kamonchanok | 2026-02-06 | 2026-02-06 | 2026-02-06 | Close | Closed | On Time
7 | Feb | RFQ | RFQ Packing | AMW QUO905 RFQ paCking | STIWA | Kamonchanok | 2026-02-09 | 2026-02-09 | 2026-02-06 | Close | Closed | On Time
7 | Feb | PACKING | Support packing | AMW 03685 Design packing concept | AEG | Kamonchanok | 2026-02-09 | 2026-02-09 | 2026-02-09 | Close | Closed | On Time
7 | Feb | RFQ | RFQ Packing | AMW QUO895 RFQ packing | Chloride | Kamonchanok | 2026-02-09 | 2026-02-10 | 2026-01-28 | Close | Closed | On Time
2 | Jan | OTHER | Training | Training Solidworks: Assembly modeling |  | Kumpon | 2026-01-05 | 2026-01-07 | 2026-01-07 | Close | Closed | On Time
3 | Jan | NPI | Sample assembly Support | MP BESS prepare torque spec | Enersys | Kumpon | 2026-01-12 | 2026-01-13 | 2026-01-13 | Close | Closed | On Time
2 | Jan | NPI | NPI Technical support | Support MP BESS training and assembly | Enersys | Kumpon | 2026-01-08 | 2026-01-15 | 2026-01-15 | Close | Closed | On Time
3 | Jan | NPI | Create drawing | Crate Drawing of Bracket BCU (Revise to use PEM) | Enersys | Kumpon | 2026-01-15 | 2026-01-15 | 2026-01-15 | Close | Closed | On Time
3 | Jan | Part DFM | Review internal DFM | AMW 03545 Review 3D data (OBC) | IES | Kumpon | 2026-01-15 | 2026-01-20 | 2026-01-19 | Close | Closed | On Time
4 | Jan | NPI | NPI Technical support | AMW 03210,03211 support assembly and trial new sampl hinge to reduce gap assembly of product | Enersys | Kumpon | 2026-01-19 | 2026-01-20 | 2026-01-19 | Close | Closed | On Time
4 | Jan | DFM Mold | Review DFM MOLD and feed back | Traco Tib Review DFM Mold of part 24100162-R00 (HeatSink sub) | Traco | Kumpon | 2026-01-19 | 2026-01-20 | 2026-01-20 | Close | Closed | On Time
4 | Jan | DFA | DFA Feedback to Customer and waiting customer review | AMW 03545 Review assembly from customer sample (OBC) | IES | Kumpon | 2026-01-20 | 2026-01-22 | 2026-01-22 | Close | Closed | On Time
4 | Jan | OTHER | Training | Training Solidworks: weldment |  | Kumpon | 2026-01-21 | 2026-01-21 | 2026-01-21 | Close | Closed | On Time
2 | Jan | MEETING | Meeting | MP BESS update status | Enersys | Bunnarak | 2026-01-05 | 2026-01-05 | 2026-01-05 | Close | Closed | On Time
2 | Jan | NPI | Quality Issue Analysis | AMW 03314 Product dimension out spec, Confirm measurement data and Jig assembly | LEACH | Bunnarak | 2026-01-05 | 2026-01-06 | 2026-01-06 | Close | Closed | On Time
2 | Jan | NPI | NPI Technical support | AMW 03314 Follow up Base plate progress to close OPL MP trouble | Enersys | Bunnarak | 2026-01-06 | 2026-01-06 | 2026-01-06 | Close | Closed | On Time
2 | Jan | NPI | NPI Technical support | AMW QUO874 support make 3D saperate part for SRC | JRI | Bunnarak | 2026-01-06 | 2026-01-07 | 2026-01-07 | Close | Closed | On Time
2 | Jan | MEETING | Meeting | AMW 03457 N0102 Numworks weekly progress | Numworks | Bunnarak | 2026-01-08 | 2026-01-08 | 2026-01-08 | Close | Closed | On Time
3 | Jan | OTHER | Training | Training Solidworks: Drawing |  | Bunnarak | 2026-01-12 | 2026-01-13 | 2026-01-13 | Close | Closed | On Time
3 | Jan | MEETING | Meeting | Numworks weekly meeting | Numworks | Bunnarak | 2026-01-15 | 2026-01-15 | 2026-01-15 | Close | Closed | On Time
3 | Jan | NPI | NPI Technical support | AMW 03457 Confirm measure point for IQC | Numworks | Bunnarak | 2026-01-15 | 2026-01-15 | 2026-01-15 | Close | Closed | On Time
3 | Jan | RFQ | RFQ | AMW-QUO874 NPI Q'ty requirment | JRI | Bunnarak | 2026-01-15 | 2026-01-16 | 2026-01-07 | Close | Closed | On Time
3 | Jan | NPI | NPI Technical support | Discuss abour assembly concept with LPI for RFQ AMW QUO818 Rev 3 |  | Bunnarak | 2026-01-16 | 2026-01-16 | 2026-01-16 | Close | Closed | On Time
3 | Jan | OTHER | Training | 7 habit |  | All | 2026-01-16 | 2026-01-16 | 2026-01-16 | Close | Closed | On Time
7 | Feb | PACKING | Design New Packaging | Review new foam top for reduce cost | Enersys | Kamonchanok | 2026-02-09 | 2026-02-10 | 2026-02-10 | Close | Closed | On Time
7 | Feb | PACKING | Design New Packaging | Trial color box at supplier | Numworks | Kamonchanok | 2026-02-10 | 2026-02-10 | 2026-02-10 | Close | Closed | On Time
7 | Feb | PACKING | Support packing | AMW 03577 Support packing 80 pcs. | FONROCHE | Kamonchanok | 2026-02-12 | 2026-02-13 | 2026-02-12 | Close | Closed | On Time
7 | Feb | PACKING | Support packing | AMW 03519 support packing | FONROCHE | Kamonchanok | 2026-02-12 | 2026-02-13 | 2026-02-12 | Close | Closed | On Time
8 | Feb | PACKING | Support packing | AMW 03457 Pilot packing | Numworks | Kamonchanok | 2026-02-16 | 2026-02-17 | 2026-02-16 | Close | Closed | On Time
7 | Feb | RFQ | RFQ Packing | AMW QUO907 RFQ Packing | MG Development | Kamonchanok | 2026-02-13 | 2026-02-13 | 2026-02-12 | Close | Closed | On Time
5 | Jan | NPI | Review OPL | OPL Meeting |  | Kumpon | 2026-01-26 | 2026-01-26 | 2026-01-26 | Close | Closed | On Time
5 | Jan | OTHER | Support register document | Adjust CAD layout of coating room |  | Kumpon | 2026-01-26 | 2026-01-27 | 2026-01-26 | Close | Closed | On Time
5 | Jan | NPI | NPI Technical support | AMW 03210, Rubber Button difficult to click, Support print 3D follow execute team design | Enersys | Kumpon | 2026-01-26 | 2026-01-27 | 2026-01-27 | Close | Closed | On Time
5 | Jan | NPI | NPI Technical support | MP BESS support assembly and test water proof | Enersys | Kumpon | 2026-01-26 | 2026-01-30 | 2026-01-30 | Close | Closed | On Time
7 | Feb | RFQ | RFQ Packing | AMW QUO906 RFQ packing | Stiwa | Kamonchanok | 2026-02-13 | 2026-02-13 | 2026-02-12 | Close | Closed | On Time
7 | Feb | RFQ | RFQ | AMW QUO906 RFQ NPI requirment | Stiwa | Kamonchanok | 2026-02-13 | 2026-02-13 | 2026-02-12 | Close | Closed | On Time
7 | Feb | RFQ | RFQ Packing | AMW QUO910 RFQ packing | Maatel | Kamonchanok | 2026-02-12 | 2026-02-13 | 2026-02-12 | Close | Closed | On Time
6 | Feb | NPI | NPI Technical support | MP BESS support assembly and test water proof | Enersys | Kumpon | 2026-02-02 | 2026-02-06 | 2026-02-06 | Close | Closed | On Time
4 | Jan | DFA | DFA Feedback to Customer and waiting customer review | AMW 03667 DFA New JRI Digital Sensor model | JRI | Bunnarak | 2026-01-19 | 2026-01-21 | 2026-01-21 | Close | Closed | On Time
4 | Jan | DFA | DFA Feedback to Customer and waiting customer review | AMW 03668 DFA New JRI Digital Sensor model | JRI | Bunnarak | 2026-01-19 | 2026-01-21 | 2026-01-21 | Close | Closed | On Time
4 | Jan | DFA | DFA Feedback to Customer and waiting customer review | AMW 03669 DFA New JRI Digital Sensor model | JRI | Bunnarak | 2026-01-21 | 2026-01-23 | 2026-01-23 | Close | Closed | On Time
4 | Jan | DFA | DFA Feedback to Customer and waiting customer review | AMW 03670 DFA New JRI Digital Sensor model | JRI | Bunnarak | 2026-01-21 | 2026-01-23 | 2026-01-23 | Close | Closed | On Time
4 | Jan | NPI | NPI Technical support | JRI confirm air leak test for hanmade part trapper for use this result to modfiy tooling | JRI | Bunnarak | 2026-01-21 | 2026-01-21 | 2026-01-21 | Close | Closed | On Time
4 | Jan | MEETING | Meeting | AMW 03457 Numworks weekly meeting | Numworks | Bunnarak | 2026-01-22 | 2026-01-22 | 2026-01-22 | Close | Closed | On Time
6 | Feb | NPI | NPI Technical support | GO to Aurum to improve grile viper warp problem | Enersys | Kumpon | 2026-02-06 | 2026-02-06 | 2026-02-06 | Close | Closed | On Time
7 | Feb | DFA | Review internal DFA | Viper 6Bays DFA review | Enersys | Kumpon | 2026-02-09 | 2026-02-13 | 2026-02-13 | Close | Closed | On Time
7 | Feb | NPI | Pilot assembly Support | AMW 03457 support preparation line | Numworks | Kumpon | 2026-02-10 | 2026-02-10 | 2026-02-10 | Close | Closed | On Time
7 | Feb | NPI | NPI Technical support | AMW 03210,03211 Trial Main door improve gap problem | Enersys | Kumpon | 2026-02-12 | 2026-02-12 | 2026-02-12 | Close | Closed | On Time
5 | Jan | NPI | NPI Technical support | AMW 03210,03211 LightGuide rattle noise. Fine the glue for use to fix lightguide | Enersys | Bunnarak | 2026-01-26 | 2026-01-26 | 2026-01-26 | Close | Closed | On Time
5 | Jan | DFA | Review internal DFA | AMW 03577 Review DFA | FONROCHE | Bunnarak | 2026-01-27 | 2026-01-28 | 2026-01-28 | Close | Closed | On Time
5 | Jan | DFM Mold | Review DFM MOLD and feed back | AMW 03577 check DFM mold document confirmation | FONROCHE | Bunnarak | 2026-01-28 | 2026-01-28 | 2026-01-28 | Close | Closed | On Time
5 | Jan | NPI | NPI Technical support | AMW 03210,03211 LightGuide rattle noise. Follow up part modify status(LightGuide) | Enersys | Bunnarak | 2026-01-29 | 2026-01-29 | 2026-01-29 | Close | Closed | On Time
5 | Jan | MEETING | Meeting | Numworks weekly meeting | Numworks | Bunnarak | 2026-01-29 | 2026-01-29 | 2026-01-29 | Close | Closed | On Time
5 | Jan | DFM Mold | Review DFM Part Drawing and feed back | Review update 3D data from RND model A14 camelet | FONROCHE | Bunnarak | 2026-01-29 | 2026-01-29 | 2026-01-29 | Close | Closed | On Time
5 | Jan | DFM Mold | Review Revised Data and Final DFM Mold Approval | Confirm revised DFM Mold of A14 camelet | FONROCHE | Bunnarak | 2026-01-30 | 2026-01-30 | 2026-01-30 | Close | Closed | On Time
6 | Feb | MEETING | Meeting | Viper assembly drawing review and feedback | Enersys | Bunnarak | 2026-02-02 | 2026-02-02 | 2026-02-02 | Close | Closed | On Time
6 | Feb | DFM Mold | DFM Feedback to Customer and waiting customer review | Pre-DFM part viper 6-Bay | Enersys | Bunnarak | 2026-02-02 | 2026-02-06 | 2026-02-06 | Close | Closed | On Time
6 | Feb | OTHER | Training | Trianing conflict management |  | All | 2026-02-05 | 2026-02-05 | 2026-02-05 | Close | Closed | On Time
7 | Feb | MEETING | Meeting | JRI weekly meeting | JRI | Bunnarak | 2026-02-09 | 2026-02-09 | 2026-02-09 | Close | Closed | On Time
7 | Feb | NPI | NPI Technical support | Support engineer confirm tolerance indication condition | JRI | Bunnarak | 2026-02-09 | 2026-02-09 | 2026-02-09 | Close | Closed | On Time
7 | Feb | DFM Mold | Review DFM Part Drawing and feed back | Share DFM 6 bay to ENG. | Enersys | Bunnarak | 2026-02-09 | 2026-02-09 | 2026-02-09 | Close | Closed | On Time
7 | Feb | NPI | Pilot assembly Support | AMW 03457 Pilot assembly | Numworks | Bunnarak | 2026-02-10 | 2026-02-13 | 2026-02-13 | Close | Closed | On Time
7 | Feb | NPI | NPI Technical support | AMW 03210,03211 Support eng simulation strength for lifting project | Enersys | Bunnarak | 2026-02-10 | 2026-02-11 | 2026-02-11 | Close | Closed | On Time
7 | Feb | NPI | NPI Technical support | JRI Liberty box support PRG confirm texture detail | JRI | Bunnarak | 2026-02-10 | 2026-02-10 | 2026-02-10 | Close | Closed | On Time
7 | Feb | RFQ | RFQ | AMW QUO907 NPI Requirment | MG Development | Bunnarak | 2026-02-13 | 2026-02-13 | 2026-02-13 | Close | Closed | On Time
8 | Feb | OTHER | Training | Training Solidworks: Surface modeling |  | Bunnarak | 2026-02-16 | 2026-02-17 | 2026-02-17 | Close | Closed | On Time
8 | Feb | MEETING | Meeting | JRI BOM overmold/ MOM as of 19/Feb 26 (Wk08) | JRI | Bunnarak | 2026-02-19 | 2026-02-19 | 2026-02-19 | Close | Closed | On Time
8 | Feb | MEETING | Meeting | Numworks weekly meeting | Numworks | Bunnarak | 2026-02-19 | 2026-02-19 | 2026-02-19 | Close | Closed | On Time
8 | Feb | NPI | NPI Technical support | Trial new insert PEM JIG at TS molymer | Enersys | Kumpon | 2026-02-16 | 2026-02-16 | 2026-02-16 | Close | Closed | On Time
8 | Feb | NPI | NPI Technical support | Support techincal meeting with Aurum | Traco | Kumpon | 2026-02-19 | 2026-02-19 | 2026-02-19 | Close | Closed | On Time
8 | Feb | NPI | NPI Technical support | Support Eng. assembly Cabinet door for check gap | Enersys | Kumpon | 2026-02-19 | 2026-02-19 | 2026-02-19 | Close | Closed | On Time
8 | Feb | RFQ | RFQ Packing | AMW QUO911 RFQ Packing | ENSISO | Kamonchanok | 2026-02-16 | 2026-02-17 | 2026-02-17 | Close | Closed | On Time
8 | Feb | PACKING | Design New Packaging | Updated Text on outer Label_Viper cabinet | Enersys | Kamonchanok | 2026-02-16 | 2026-02-17 | 2026-02-17 | Close | Closed | On Time
8 | Feb | PACKING | Design New Packaging | Add ESD Tray for PCB & Top cover AMW 03457 in process | Numworks | Kamonchanok | 2026-02-18 | 2026-02-18 | 2026-02-18 | Close | Closed | On Time
8 | Feb | PACKING | Design New Packaging | Fonroche A14 - AMW 03577 - Packaging | Numworks | Kamonchanok | 2026-02-18 | 2026-02-18 | 2026-02-18 | Close | Closed | On Time
8 | Feb | RFQ | RFQ Packing | AMW QUO914 RFQ Packing | ML Optic | Kamonchanok | 2026-02-18 | 2026-02-19 | 2026-02-18 | Close | Closed | On Time
8 | Feb | PACKING | Design New Packaging | Packing internal process_IES 50 KW | IES | Kamonchanok | 2026-02-18 | 2026-02-19 | 2026-02-19 | Close | Closed | On Time
8 | Feb | PACKING | Design New Packaging | updated Text on outer Label_Viper cabinet Rev2 | Enersys | Kamonchanok | 2026-02-19 | 2026-02-19 | 2026-02-19 | Close | Closed | On Time
8 | Feb | PACKING | Design New Packaging | Design new box for stand viper | Enersys | Kamonchanok | 2026-02-19 | 2026-02-20 | 2026-02-20 | Close | Closed | On Time
8 | Feb | NPI | NPI Technical support | AMW 03457 document registration Parameter setting of Shrink warp machine | Numworks | Kamonchanok | 2026-02-19 | 2026-02-20 | 2026-02-20 | Close | Closed | On Time
9 | Feb | PACKING | Design New Packaging | AMW 03211, 03210 follow up comment new box for stand viper | Enersys | Kamonchanok | 2026-02-23 | 2026-02-25 | 2026-02-25 | Close | Closed | On Time
9 | Feb | PACKING | Design New Packaging | AMW03457 Add ESD Tray for PCB & Top cover AMW 03457 in process | Numworks | Kamonchanok | 2026-02-23 | 2026-02-24 | 2026-02-24 | Close | Closed | On Time
9 | Feb | RFQ | RFQ Packing | AMW QUO918 RFQ Packing | Bernina | Kamonchanok | 2026-02-24 | 2026-02-25 | 2026-02-24 | Close | Closed | On Time
9 | Feb | PACKING | Design New Packaging | follow up TRACO TIB project - packaging, Large Packing Box (L) and Small Packing Box (S) | Traco | Kamonchanok | 2026-02-24 | 2026-02-25 | 2026-02-25 | Close | Closed | On Time
9 | Feb | RFQ | RFQ Packing | AMW QUO921 RFQ Packing | Stiwa | Kamonchanok | 2026-02-26 | 2026-02-27 | 2026-02-26 | Close | Closed | On Time
9 | Feb | PACKING | Design New Packaging | updated Text on outer Label_Viper cabinet Rev2 - waiting sample | Enersys | Kamonchanok | 2026-02-27 | 2026-02-27 | 2026-02-27 | Close | Closed | On Time
8 | Feb | MEETING | Meeting | JRI BOM overmold/ MOM as of 19/Feb 26 (Wk08) | JRI | Thiti | 2026-02-19 | 2026-02-19 | 2026-02-19 | Close | Closed | On Time
8 | Feb | DFM Mold | Review DFM MOLD and feed back | Review DFM of IM70/IM65 of MAATEL | Maatel | Thiti | 2026-02-18 | 2026-02-18 | 2026-02-18 | Close | Closed | On Time
8 | Feb | NPI | NPI Technical support | Meeting with Supplier and MAATEL for IM70/IM65 | Maatel | Thiti | 2026-02-18 | 2026-02-18 | 2026-02-18 | Close | Closed | On Time
8 | Feb | NPI | Pilot assembly Support | Observe Pre-audit of Numworks | Numworks | Thiti | 2026-02-18 | 2026-02-18 | 2026-02-18 | Close | Closed | On Time
8 | Feb | NPI | NPI Technical support | Discuss with Sour about Rubber 70A | Enersys | Thiti | 2026-02-18 | 2026-02-18 | 2026-02-18 | Close | Closed | On Time
8 | Feb | OTHER | 5S meeting | 5S Meeting |  | Thiti | 2026-02-18 | 2026-02-18 | 2026-02-18 | Close | Closed | On Time
8 | Feb | MEETING | Meeting | Numworks weekly meeting | Numworks | Thiti | 2026-02-19 | 2026-02-19 | 2026-02-19 | Close | Closed | On Time
8 | Feb | DFA | Initial review custmer data for DFA | Study component material for overmolding | JRI | Thiti | 2026-02-18 | 2026-02-20 | 2026-02-20 | Close | Closed | On Time
8 | Feb | DFM Mold | Review DFM MOLD and feed back | Meeting with Mold maker for overmolding | JRI | Thiti | 2026-02-20 | 2026-02-20 | 2026-02-20 | Close | Closed | On Time
9 | Feb | NPI | NPI Technical support | Support Eng. Trial injection of GL0016722-Case Viper for short mold and Gap between both part | Enersys | Thiti | 2026-02-23 | 2026-02-23 | 2026-02-23 | Close | Closed | On Time
9 | Feb | NPI | NPI Technical support | Review PackingSTD of Face JRI | JRI | Thiti | 2026-02-24 | 2026-02-24 | 2026-02-24 | Close | Closed | On Time
9 | Feb | NPI | NPI Technical support | Review technical data of MAATEL | Maatel | Thiti | 2026-02-24 | 2026-02-24 | 2026-02-24 | Close | Closed | On Time
9 | Feb | NPI | NPI Technical support | Confirm part Face of JRI with SQE about Texture | JRI | Thiti | 2026-02-24 | 2026-02-24 | 2026-02-24 | Close | Closed | On Time
9 | Feb | NPI | NPI Technical support | AMW 03457 Techinical meeting for Battery Adhesive New Design and Foam Screen Protection | Numworks | Thiti | 2026-02-25 | 2026-02-25 | 2026-02-25 | Close | Closed | On Time
9 | Feb | NPI | NPI Technical support | AMW 03457 Techinical meeting for new project charging dock | Numworks | Thiti | 2026-02-25 | 2026-02-25 | 2026-02-25 | Close | Closed | On Time
9 | Feb | NPI | NPI Technical support | AMW 03457 Follow up supplier about improve dust on protection film | Numworks | Thiti | 2026-02-23 | 2026-02-26 | 2026-02-26 | Close | Closed | On Time
9 | Feb | NPI | PreSerise assembly Support | AMW 03457 Support Numworks pre series audit 24-25-Feb | Numworks | Thiti | 2026-02-24 | 2026-02-26 | 2026-02-26 | Close | Closed | On Time
9 | Feb | NPI | NPI Technical support | Conference call YPC-AMW-NUMWORK | Numworks | Thiti | 2026-02-26 | 2026-02-26 | 2026-02-26 | Close | Closed | On Time
9 | Feb | OTHER | 5S meeting | 5S Meeting |  | Thiti | 2026-02-26 | 2026-02-26 | 2026-02-26 | Close | Closed | On Time
9 | Feb | MEETING | Meeting | JRI weekly meeting | JRI | Bunnarak | 2026-02-23 | 2026-02-23 | 2026-02-23 | Close | Closed | On Time
9 | Feb | NPI | NPI Technical support | (VIPER) Engineering Study for VIPER Power Button Actuation Issue | Enersys | Bunnarak | 2026-02-23 | 2026-02-24 | 2026-02-23 | Close | Closed | On Time
9 | Feb | NPI | NPI Technical support | Support SRC help to review overmold quotation | JRI | Bunnarak | 2026-02-24 | 2026-02-25 | 2026-02-24 | Close | Closed | On Time
9 | Feb | NPI | NPI Technical support | AMW 03457 Techinical meeting for Battery Adhesive New Design and Foam Screen Protection | Numworks | Bunnarak | 2026-02-25 | 2026-02-25 | 2026-02-25 | Close | Closed | On Time
9 | Feb | NPI | NPI Technical support | AMW 03457 Techinical meeting for new project charging dock | Numworks | Bunnarak | 2026-02-25 | 2026-02-25 | 2026-02-25 | Close | Closed | On Time
9 | Feb | NPI | NPI Technical support | Conference call YPC-AMW-NUMWORK | Numworks | Bunnarak | 2026-02-26 | 2026-02-26 | 2026-02-26 | Close | Closed | On Time
9 | Feb | NPI | NPI Technical support | Support Quality simulation White key for checking idea reduce rib for improve button cutting | Numworks | Bunnarak | 2026-02-26 | 2026-02-27 | 2026-02-27 | Close | Closed | On Time
9 | Feb | NPI | PreSerise assembly Support | AMW 03457 Support numworks pre series wrap process | Numworks | Bunnarak | 2026-02-27 | 2026-02-27 | 2026-02-27 | Close | Closed | On Time
9 | Feb | NPI | NPI Technical support | Fine spec 3D prinitng machine for integration team |  | Kumpon | 2026-02-24 | 2026-02-24 | 2026-02-24 | Close | Closed | On Time
9 | Feb | NPI | PreSerise assembly Support | AMW 03457 Support Numworks pre series audit 24-25-Feb | Numworks | Kumpon | 2026-02-24 | 2026-02-26 | 2026-02-26 | Close | Closed | On Time
9 | Feb | NPI | NPI Technical support | AMW 03457 Print 3D base support assembly for line production | Numworks | Kumpon | 2026-02-24 | 2026-02-26 | 2026-02-25 | Close | Closed | On Time
9 | Feb | PACKING | Design New Packaging | AMW 03577 Delete ESD TRAY | Maatel | Kamonchanok | 2026-02-25 | 2026-02-26 | 2026-02-26 | Close | Closed | On Time
10 | Mar | RFQ | RFQ Packing | AMW QUO915 RFQ Packing | Stiwa | Kamonchanok | 2026-03-02 | 2026-03-03 | 2026-03-03 | Close | Closed | On Time
10 | Mar | RFQ | RFQ Packing | AMW-QUO925 NEW VIPER STAND GL0025010-0000 | Enersys | Kamonchanok | 2026-03-03 | 2026-03-06 | 2026-03-03 | Close | Closed | On Time
10 | Mar | RFQ | RFQ Packing | AMW-QUO920 Rev01.01_project 1650W power supply for Fulham | Fulham | Kamonchanok | 2026-03-03 | 2026-03-04 | 2026-03-03 | Close | Closed | On Time
10 | Mar | OTHER | Training | Training sollidworks |  | Kamonchanok | 2026-03-04 | 2026-03-06 | 2026-03-06 | Close | Closed | On Time
10 | Mar | PACKING | Support packing | AMW 03534 PCBA Supoport sample packing 10 pcs. |  | Kamonchanok | 2026-03-05 | 2026-03-06 | 2026-03-06 | Close | Closed | On Time
10 | Mar | RFQ | RFQ Packing | AMW QUO925 packaging RFQ |  | Kamonchanok | 2026-03-04 | 2026-03-06 | 2026-03-04 | Close | Closed | On Time
10 | Mar | NPI | NPI Technical support | compair 3D Assemble AMW 03517 REV 11.5 with EN-GL0015879-00 R0 |  | kumpon | 2026-03-02 | 2026-03-02 | 2026-03-02 | Close | Closed | On Time
10 | Mar | NPI | NPI Technical support | Compair spec 3D prinitng machine for integration team |  | kumpon | 2026-03-02 | 2026-03-03 | 2026-03-03 | Close | Closed | On Time
10 | Mar | NPI | NPI Technical support | Design concept assemble anti slip number |  | kumpon | 2026-03-02 | 2026-03-03 | 2026-03-03 | Close | Closed | On Time
10 | Mar | NPI | NPI Technical support | Confirm price information of filament fir printing support GL0016810 | Enersys | Kumpon | 2026-03-03 | 2026-03-03 | 2026-03-03 | Close | Closed | On Time
10 | Mar | OTHER | Training | Training Solidworks: Drawing |  | kumpon | 2026-03-04 | 2026-03-05 | 2026-03-05 | Close | Closed | On Time
10 | Mar | OTHER | Training | Training sollidworks |  | Thiti | 2026-03-04 | 2026-03-05 | 2026-03-05 | Close | Closed | On Time
10 | Mar | NPI | NPI Technical support | Discuss about the custumer issue with the anti-slip pad | Numworks | Thiti | 2026-03-06 | 2026-03-06 | 2026-03-06 | Close | Closed | On Time
10 | Mar | MEETING | Meeting | Numwork weekly progress | Numworks | Bunnarak | 2026-03-05 | 2026-03-05 | 2026-03-05 | Close | Closed | On Time
10 | Mar | OTHER | Interview candidate new member | Interview for the position of NPI |  | Bunnarak | 2026-03-05 | 2026-03-05 | 2026-03-05 | Close | Closed | On Time
10 | Mar | OTHER | Create standard document | List mandatory for manufacturing and rfq |  | Bunnarak | 2026-03-05 | 2026-03-06 | 2026-03-06 | Close | Closed | On Time
10 | Mar | NPI | NPI Technical support | Follow up with SRC about button power (rubber) | Enersys | Thiti | 2026-03-06 | 2026-03-06 | 2026-03-06 | Close | Closed | On Time
10 | Mar | NPI | NPI Technical support | Support technical discuss with supplier Harvard about JRI part | JRI | Thiti | 2026-03-06 | 2026-03-06 | 2026-03-06 | Close | Closed | On Time
11 | Mar | MEETING | Meeting | JRI weekly progress | JRI | Thiti | 2026-03-09 | 2026-03-09 | 2026-03-09 | Close | Closed | On Time
11 | Mar | NPI | Review JIG concept | Confirm JIG attached New Material NW-Foam Screen | Numworks | Thiti | 2026-03-09 | 2026-03-09 | 2026-03-09 | Close | Closed | On Time
11 | Mar | NPI | NPI Technical support | Trial assembly New material of NW-Foam Screen | Numworks | Thiti | 2026-03-09 | 2026-03-09 | 2026-03-09 | Close | Closed | On Time
11 | Mar | NPI | NPI Technical support | Follow up assembly of Viper-Case for confirm gap | Enersys | Thiti | 2026-03-09 | 2026-03-09 | 2026-03-09 | Close | Closed | On Time
11 | Mar | NPI | NPI Technical support | Review customer process for attach new NW-Batt Adhesive | Numwoks | Thiti | 2026-03-10 | 2026-03-10 | 2026-03-10 | Close | Closed | On Time
11 | Mar | NPI | NPI Technical support | Discuss with tooling team about New jig NW-Batt-Adhesive | Numworks | Thiti | 2026-03-10 | 2026-03-10 | 2026-03-10 | Close | Closed | On Time
11 | Mar | NPI | NPI Technical support | Finding dot gauge for Quality department | Numworks | Thiti | 2026-03-10 | 2026-03-10 | 2026-03-10 | Close | Closed | On Time
11 | Mar | NPI | NPI Technical support | Found defect(dot) after visual inspection | Numworks | Thiti | 2026-03-11 | 2026-03-11 | 2026-03-11 | Close | Closed | On Time
11 | Mar | NPI | NPI Technical support | Confirm NW-Slip pad after improvement | Numworks | Thiti | 2026-03-11 | 2026-03-11 | 2026-03-11 | Close | Closed | On Time
11 | Mar | MEETING | Meeting | Numworks weekly meeting | Numworks | Thiti | 2026-03-12 | 2026-03-12 | 2026-03-12 | Close | Closed | On Time
11 | Mar | NPI | NPI Technical support | Trial attached new NW-Batt Adhesive | Numworks | Thiti | 2026-03-13 | 2026-03-13 | 2026-03-13 | Close | Closed | On Time
11 | Mar | MEETING | meeting | Meeting discussion about New jig of NW-Foam Screen | Numworks | Thiti | 2026-03-13 | 2026-03-13 | 2026-03-13 | Close | Closed | On Time
11 | Mar | NPI | NPI Technical support | Confirm dust of NW model with Dot gauge | Numworks | Thiti | 2026-03-13 | 2026-03-13 | 2026-03-13 | Close | Closed | On Time
11 | Mar | NPI | NPI Technical support | Discussion about NW-Slip pad | Numworks | Thiti | 2026-03-13 | 2026-03-13 | 2026-03-13 | Close | Closed | On Time
11 | Mar | PACKING | Support packing | Modify label template by remove AMW text on label and 2D barcode | Numworks | Kamonchanok | 2026-03-11 | 2026-03-11 | 2026-03-11 | Close | Closed | On Time
11 | Mar | RFQ | RFQ Packing | AMW QUO929 RFQ packing | Pro Glove | Kamonchanok | 2026-03-12 | 2026-03-13 | 2026-03-13 | Close | Closed | On Time
11 | Mar | PACKING | Support packing | Pack box Cabinet and foam final design sent to customer | Enersys | Kamonchanok | 2026-03-13 | 2026-03-13 | 2026-03-13 | Close | Closed | On Time
11 | Mar | PACKING | Design New Packaging | Request quotation part ESD BOX snd Oink foam AMW 03512/03513 |  | Kamonchanok | 2026-03-13 | 2026-03-13 | 2026-03-13 | Close | Closed | On Time
11 | Mar | RFQ | RFQ Packing | AMW QUO917 VIPER 6 BAY CABINET | Enersys | Kamonchanok | 2026-03-13 | 2026-03-13 | 2026-03-13 | Close | Closed | On Time
11 | Mar | PACKING | Design New Packaging | Std packing in IBM: AMW 03577 & AMW 03577 FOAM |  | Kamonchanok | 2026-03-12 | 2026-03-13 | 2026-03-13 | Close | Closed | On Time
11 | Mar | MEETING | Meeting | JRI weekly progress | JRI | Bunnarak | 2026-03-09 | 2026-03-09 | 2026-03-09 | Close | Closed | On Time
11 | Mar | OTHER | Visit Exhibition | Join simulation exhibitor at AppliCAD Innovation Center |  | Bunnarak | 2026-03-10 | 2026-03-10 | 2026-03-10 | Close | Closed | On Time
11 | Mar | NPI | NPI Technical support | Support IND team simulation strength for Cutting key jig | Numworks | Bunnarak | 2026-03-11 | 2026-03-12 | 2026-03-12 | Close | Closed | On Time
11 | Mar | MEETING | Meeting | Fairland water pump progress meeting | Fairland | Bunnarak | 2026-03-13 | 2026-03-13 | 2026-03-13 | Close | Closed | On Time
11 | Mar | RFQ | RFQ | AMW QUO929 RFQ integration requirement | Pro Glove | Bunnarak | 2026-03-12 | 2026-03-13 | 2026-03-13 | Close | Closed | On Time
11 | Mar | MEETING | Meeting | Fairland water pump progress meeting | Fairland | Bunnarak | 2026-03-12 | 2026-03-12 | 2026-03-12 | Close | Closed | On Time
10 | Mar | NPI | NPI Technical support | Support OBC model | IES | Kumpon | 2026-03-06 | 2026-03-06 | 2026-03-06 | Close | Closed | On Time
11 | Mar | OTHER | Visit Exhibition | Join simulation exhibitor at AppliCAD Innovation Center |  | Kumpon | 2026-03-10 | 2026-03-10 | 2026-03-10 | Close | Closed | On Time
11 | Mar | MEETING | Meeting | Update detail for Fairland water pump progress | Fairland | Kumpon | 2026-03-12 | 2026-03-13 | 2026-03-13 | Close | Closed | On Time
11 | Mar | MEETING | Meeting | Fairland water pump progress meeting | Fairland | Kumpon | 2026-03-12 | 2026-03-12 | 2026-03-12 | Close | Closed | On Time
11 | Mar | MEETING | Meeting | Fairland water pump progress meeting | Fairland | Kumpon | 2026-03-13 | 2026-03-13 | 2026-03-13 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Join to visit new supplier SINGLE POINT ENGINEERING COMPANY with Qua and SRC |  | Kumpon | 2026-03-18 | 2026-03-18 | 2026-03-18 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Follow progress defect of Numworks preseries | Numworks | Thiti | 2026-03-16 | 2026-03-16 | 2026-03-16 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Follow progress defect of Numworks preseries | Numworks | Bunnarak | 2026-03-16 | 2026-03-16 | 2026-03-16 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Follow progress defect of Numworks preseries | Numworks | Kumpon | 2026-03-16 | 2026-03-16 | 2026-03-16 | Close | Closed | On Time
11 | Mar | PACKING | Support packing | AMW 03368 (packing AEG) | AEG | Kamonchanok | 2026-03-10 | 2026-03-10 | 2026-03-10 | Close | Closed | On Time
11 | Mar | PACKING | Support packing | AMW 03519 (packing + label) |  | Kamonchanok | 2026-03-10 | 2026-03-12 | 2026-03-12 | Close | Closed | On Time
11 | Mar | PACKING | Support packing | AMW 03495 (packing) |  | Kamonchanok | 2026-03-12 | 2026-03-12 | 2026-03-12 | Close | Closed | On Time
11 | Mar | PACKING | Support packing | AMW 03457 (LABEL) |  | Kamonchanok | 2026-03-11 | 2026-03-11 | 2026-03-11 | Close | Closed | On Time
11 | Mar | PACKING | Support packing | AMW 03511 (review packing support customer ) |  | Kamonchanok | 2026-03-11 | 2026-03-11 | 2026-03-11 | Close | Closed | On Time
11 | Mar | PACKING | Support packing | Test sample packing Traco TIB 80 120 240 480 |  | Kamonchanok | 2026-03-11 | 2026-03-11 | 2026-03-11 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Review Numworks PreSeries reworks process |  | Kumpon | 2026-03-16 | 2026-03-16 | 2026-03-16 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Fine hot glue for attached Lightguide with PCBA | Enersys | Kumpon | 2026-03-17 | 2026-03-17 | 2026-03-17 | Close | Closed | On Time
12 | Mar | DFM Mold | Review DFM Part Drawing and feed back | DFM part Metal for BouchonCopletNanoSPY | JRI | Kumpon | 2026-03-18 | 2026-03-20 | 2026-03-20 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Drawing new factory layout | Fairland | Kumpon | 2026-03-19 | 2026-03-20 | 2026-03-20 | Close | Closed | On Time
13 | Mar | OTHER | Training | Training SolidWorks Simulation |  | Kumpon | 2026-03-23 | 2026-03-25 | 2026-03-25 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Discuss with tesa for new material of battery adhesive | Numworks | Thiti | 2026-03-16 | 2026-03-16 | 2026-03-16 | Close | Closed | On Time
17 | Apr | OTHER | Training | Training SolidWorks Simulation |  | Thiti | 2026-04-20 | 2026-04-22 | 2026-04-22 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Review Numworks PreSeries reworks process | Numworks | Thiti | 2026-03-16 | 2026-03-16 | 2026-03-16 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Assembly confirm light guide with PCBA by double side tape | Enersys | Thiti | 2026-03-16 | 2026-03-16 | 2026-03-16 | Close | Closed | On Time
12 | Mar | DFM Mold | Review DFM Part Drawing and feed back | DFM part plastic for BouchonCopletNanoSPY | JRI | Thiti | 2026-03-17 | 2026-03-20 | 2026-03-20 | Close | Closed | On Time
12 | Mar | DFM Mold | Review DFM MOLD and feed back | Discuss pre-mold DFM with HARVARD | JRI | Thiti | 2026-03-18 | 2026-03-18 | 2026-03-18 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Measure NW-defect about step between SC protection and TopCover | Numworks | Thiti | 2026-03-18 | 2026-03-18 | 2026-03-18 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Review new Foam Screen jig concep | Numworks | Thiti | 2026-03-18 | 2026-03-18 | 2026-03-18 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Foam Screen Jig Discussion | Numworks | Thiti | 2026-03-19 | 2026-03-19 | 2026-03-19 | Close | Closed | On Time
12 | Mar | MEETING | Meeting | Numworks weekly progress | Numworks | Thiti | 2026-03-19 | 2026-03-19 | 2026-03-19 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Review measurement method with Quality team and adjust measurement program due to method is not proper | Numworks | Thiti | 2026-03-19 | 2026-03-19 | 2026-03-19 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Discuss with supplier anti slip pad about appearance comment | Numworks | Thiti | 2026-03-20 | 2026-03-20 | 2026-03-20 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Support NW-Shrink warp for drop test 60 pcs | Numworks | Thiti | 2026-03-20 | 2026-03-20 | 2026-03-20 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Technical Meeting with Foamtec about NW-Slip pad how to imrprove | Numworks | Thiti | 2026-03-20 | 2026-03-20 | 2026-03-20 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Support assembly NW with Top Cover after improved | Numworks | Thiti | 2026-03-20 | 2026-03-20 | 2026-03-20 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Review Numworks PreSeries reworks process | Numworks | Bunnarak | 2026-03-16 | 2026-03-16 | 2026-03-16 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Support SRC review technical term of overmold quotation | JRI | Bunnarak | 2026-03-16 | 2026-03-16 | 2026-03-16 | Close | Closed | On Time
12 | Mar | DFA | Initial review custmer data for DFA | DFA for BouchonCopletNanoSPY | JRI | Bunnarak | 2026-03-17 | 2026-03-20 | 2026-03-20 | Close | Closed | On Time
12 | Mar | DFM Mold | Review DFM MOLD and feed back | Discuss pre-mold DFM with HARVARD | JRI | Bunnarak | 2026-03-18 | 2026-03-18 | 2026-03-18 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | Request PRG confirm about soft mold made for BonChon | JRI | Bunnarak | 2026-03-18 | 2026-03-19 | 2026-03-18 | Close | Closed | On Time
12 | Mar | MEETING | Meeting | Numworks weekly progress | Numworks | Bunnarak | 2026-03-19 | 2026-03-19 | 2026-03-19 | Close | Closed | On Time
12 | Mar | RFQ | RFQ Packing | AMW-QUO931(PCBA) RFQ packing | Satys Electronic | Kamonchanok | 2026-03-16 | 2026-03-16 | 2026-03-16 | Close | Closed | On Time
12 | Mar | NPI | NPI Technical support | AMW 03457 Technical support for drop test | Numworks | Kamonchanok | 2026-03-16 | 2026-03-18 | 2026-03-17 | Close | Closed | On Time
12 | Mar | PACKING | Design New Packaging | New Fonroche projects - Packing concepts | Fonroche | Kamonchanok | 2026-03-17 | 2026-03-18 | 2026-03-17 | Close | Closed | On Time
12 | Mar | PACKING | Design New Packaging | New Fonroche projects - Packing concepts AMW 03520 and AMW 03521 | Fonroche | Kamonchanok | 2026-03-17 | 2026-03-18 | 2026-03-17 | Close | Closed | On Time
12 | Mar | RFQ | RFQ Packing | AMW-QUO932(M-Part) RFQ packing | Radio Energig | Kamonchanok | 2026-03-18 | 2026-03-19 | 2026-03-17 | Close | Closed | On Time
12 | Mar | PACKING | Support packing | Support packing Numworks for drop test, 60 box | Numworks | Kamonchanok | 2026-03-19 | 2026-03-20 | 2026-03-20 | Close | Closed | On Time
13 | Mar | RFQ | RFQ Packing | AMW-QUO933 (BoxBuild) RFQ packing | Butronik | Kamonchanok | 2026-03-23 | 2026-03-24 | 2026-03-23 | Close | Closed | On Time
14 | Mar | RFQ | RFQ Packing | AMW-QUO934(PCBA) RFQ packing | Synus power | Kamonchanok | 2026-03-30 | 2026-03-31 | 2026-03-23 | Close | Closed | On Time
13 | Mar | NPI | NPI Technical support | Follow up Numworks master carton difficult to close | Numworks | Kamonchanok | 2026-03-23 | 2026-03-24 | 2026-03-24 | Close | Closed | On Time
13 | Mar | RFQ | RFQ Packing | AMW-QUO935 RFQ packing | Fulham | Kamonchanok | 2026-03-23 | 2026-03-24 | 2026-03-24 | Close | Closed | On Time
13 | Mar | PACKING | Design New Packaging | AMW 03513,03512 SMT, update part packing in process_IES 50kw | IES | Kamonchanok | 2026-03-23 | 2026-03-24 | 2026-03-23 | Close | Closed | On Time
13 | Mar | PACKING | Design New Packaging | New Fonroche projects - Packing concepts, AMW 03519/03520/03521/03518/03579 | Fonroche | Kamonchanok | 2026-03-24 | 2026-03-25 | 2026-03-24 | Close | Closed | On Time
13 | Mar | PACKING | Design New Packaging | Request sample FOAM SUPPORT STAND USA | Enersys | Kamonchanok | 2026-03-24 | 2026-03-25 | 2026-03-25 | Close | Closed | On Time
13 | Mar | PACKING | Design New Packaging | New Fonroche projects - Packing concepts, AMW 03577 | Fonroche | Kamonchanok | 2026-03-25 | 2026-03-25 | 2026-03-25 | Close | Closed | On Time
13 | Mar | PACKING | Design New Packaging | Updated packing proposals of the Fonroche, with the sticker DO NOT STACK on pallet AMW 03518/03519/03520/03521/03579/03577 | Fonroche | Kamonchanok | 2026-03-24 | 2026-03-25 | 2026-03-25 | Close | Closed | On Time
13 | Mar | NPI | NPI Technical support | Join to support Quality about master carton drop test | Numworks | Kamonchanok | 2026-03-27 | 2026-03-27 | 2026-03-27 | Close | Closed | On Time
13 | Mar | NPI | NPI Technical support | Pre DFM mold meeting for overmold project supplier PowerMold | JRI | Bunnarak | 2026-03-23 | 2026-03-23 | 2026-03-23 | Close | Closed | On Time
13 | Mar | NPI | NPI Technical support | Follow up Numworks master carton difficult to close | Numworks | Bunnarak | 2026-03-23 | 2026-03-24 | 2026-03-23 | Close | Closed | On Time
13 | Mar | NPI | NPI Technical support | Feedback about DFM mold engineering perspective | Fonroche | Bunnarak | 2026-03-24 | 2026-03-25 | 2026-03-25 | Close | Closed | On Time
13 | Mar | NPI | NPI Technical support | define the critical dimension for our assy of all raw material Numworks | Numworks | Bunnarak | 2026-03-24 | 2026-03-25 | 2026-03-25 | Close | Closed | On Time
13 | Mar | NPI | NPI Technical support | Mold Maker for Over Molding JRI Green Digital Sensor the NPI technical assessment below | JRI | Bunnarak | 2026-03-25 | 2026-03-25 | 2026-03-25 | Close | Closed | On Time
13 | Mar | NPI | NPI Technical support | Finding the root cause and preventive action about problem the Screen protection value over spec | Numworks | Bunnarak | 2026-03-25 | 2026-03-25 | 2026-03-25 | Close | Closed | On Time
13 | Mar | NPI | NPI Technical support | Support with eng validate packbox with new foam support for new short stand cabinet viper | Enersys | Bunnarak | 2026-03-27 | 2026-03-27 | 2026-03-27 | Close | Closed | On Time
13 | Mar | NPI | NPI Technical support | Follow up Numworks master carton difficult to close | Numworks | Thiti | 2026-03-23 | 2026-03-24 | 2026-03-24 | Close | Closed | On Time
13 | Mar | MEETING | Meeting | JRI weekly progress | JRI | Thiti | 2026-03-23 | 2026-03-23 | 2026-03-23 | Close | Closed | On Time
13 | Mar | NPI | NPI Technical support | Pre DFM mold meeting for overmold project supplier PowerMold | JRI | Thiti | 2026-03-23 | 2026-03-23 | 2026-03-23 | Close | Closed | On Time
13 | Mar | NPI | NPI Technical support | Follow up anti slip pad after improve appearance surface | Numworks | Thiti | 2026-03-25 | 2026-03-25 | 2026-03-25 | Close | Closed | On Time
13 | Mar | NPI | NPI Technical support | Finding the root cause and preventive action about problem the Screen protection value over spec | Numworks | Thiti | 2026-03-25 | 2026-03-25 | 2026-03-25 | Close | Closed | On Time
13 | Mar | MEETING | Meeting | Numworks weekly progress | Numworks | Thiti | 2026-03-26 | 2026-03-26 | 2026-03-26 | Close | Closed | On Time
13 | Mar | NPI | NPI Technical support | Foam Screen Jig Trial assembly | Numworks | Thiti | 2026-03-27 | 2026-03-27 | 2026-03-27 | Close | Closed | On Time
13 | Mar | NPI | NPI Technical support | Join to support Quality about master carton drop test | Numworks | Thiti | 2026-03-27 | 2026-03-27 | 2026-03-27 | Close | Closed | On Time
14 | Mar | MEETING | Meeting | Packaging job transfer |  | Kamonchanok | 2026-03-30 | 2026-03-30 | 2026-03-30 | Close | Closed | On Time
14 | Mar | RFQ | RFQ Packing | AMW QUO820 rev03 RFQ packing |  | Kamonchanok | 2026-03-31 | 2026-04-01 | 2026-03-31 | Close | Closed | On Time
14 | Mar | PACKING | Design New Packaging | AMW 03457 provide usage for pallet 100*120 |  | Kamonchanok | 2026-03-30 | 2026-03-31 | 2026-03-30 | Close | Closed | On Time
14 | Mar | RFQ | RFQ Packing | AMW QUO936 RFQ packing |  | Kamonchanok | 2026-03-30 | 2026-03-31 | 2026-03-31 | Close | Closed | On Time
14 | Apr | NPI | NPI Technical support | AMW 03577 create packing proposal send to tech-Eng for request customer |  | Bunnarak | 2026-04-01 | 2026-04-02 | 2026-04-02 | Close | Closed | On Time
14 | Mar | NPI | NPI Technical support | AMW 03577 customer support audit | Fonroche | Bunnarak | 2026-03-31 | 2026-04-02 | 2026-04-02 | Close | Closed | On Time
14 | Mar | NPI | NPI Technical support | Support JRI liberty box pre series | JRI | Bunnarak | 2026-03-31 | 2026-04-03 | 2026-04-03 | Close | Closed | On Time
14 | Mar | MEETING | Meeting | Packaging job transfer |  | Thiti | 2026-03-30 | 2026-03-30 | 2026-03-30 | Close | Closed | On Time
14 | Mar | NPI | NPI Technical support | AMW 03457 MP monitoring | Numworks | Thiti | 2026-03-31 | 2026-04-03 | 2026-04-03 | Close | Closed | On Time
14 | Apr | NPI | NPI Technical support | Numwork Confrim sample drop test with QA | Numworks | Thiti | 2026-04-01 | 2026-04-01 | 2026-04-01 | Close | Closed | On Time
14 | Apr | PACKING | Support packing | Design packing and finding part for AMW-03579 | FONROCHE | Thiti | 2026-04-01 | 2026-04-01 | 2026-04-01 | Close | Closed | On Time
14 | Apr | NPI | NPI Technical support | Air leak test after get JRI-Trapp modification | JRI | Thiti | 2026-04-01 | 2026-04-01 | 2026-04-01 | Close | Closed | On Time
14 | Apr | NPI | NPI Technical support | COnfirm part trap after modify | JRI | Thiti | 2026-04-02 | 2026-04-03 | 2026-04-01 | Close | Closed | On Time
14 | Apr | MEETING | Meeting | Numworks weekly progress | Numworks | Thiti | 2026-04-02 | 2026-04-02 | 2026-04-02 | Close | Closed | On Time
14 | Apr | PACKING | Support packing | Design packing and finding part for AMW-03256-R.BD | Gutor | Thiti | 2026-04-02 | 2026-04-02 | 2026-04-02 | Close | Closed | On Time
14 | Apr | NPI | NPI Technical support | Confirm NEW foam-C with density 22 | Numworks | Thiti | 2026-04-02 | 2026-04-02 | 2026-04-02 | Close | Closed | On Time
14 | Apr | NPI | NPI Technical support | Confirm NW-Anti Slip pad with new color | Numworks | Thiti | 2026-04-02 | 2026-04-02 | 2026-04-02 | Close | Closed | On Time
19 | May | RFQ | RFQ Packing | AMW-QUO947 Rev01.01 - project T411 part 2 for LEACH RFQZ Packing | Leach | Bunnarak | 2026-05-06 | 2026-05-08 | 2026-05-07 | Close | Closed | On Time
19 | May | PACKING | Design New Packaging | RFQ for Tray ESD TRAY AMW 03721 confirmation tray plug nano | JRI | Bunnarak | 2026-05-07 | 2026-05-08 | 2026-05-07 | Close | Closed | On Time
19 | May | RFQ | RFQ Packing | AMW-QUO951 Rev01.01 RFQ packing | Fonroche | Bunnarak | 2026-05-06 | 2026-05-08 | 2026-05-07 | Close | Closed | On Time
19 | May | PACKING | Design New Packaging | Confirm Internal packaging for PCBA external packaging for Module and Cabinet for viper 600v. | Enersys | Bunnarak | 2026-05-08 | 2026-05-12 | 2026-05-12 | Close | Closed | On Time
19 | May | RFQ | RFQ Packing | AMW-QUO507 Rev.06.01 for Numworks RFQ packing | Numworks | Bunnarak | 2026-05-07 | 2026-05-13 | 2026-05-13 | Close | Closed | On Time
20 | May | MEETING | meeting | BAT - Numworks low voltage meeting | Numworks | Bunnarak | 2026-05-15 | 2026-05-15 | 2026-05-15 | Close | Closed | On Time
19 | May | PACKING | Support packing | Design Packing concept of AMW 03716 & 03718 | Maatel | Thiti | 2026-05-05 | 2026-05-06 | 2026-05-06 | Close | Closed | On Time
19 | May | PACKING | Support packing | Design Packing concept of AMW 03520 & 03521 | Fonroche | Thiti | 2026-05-05 | 2026-05-06 | 2026-05-06 | Close | Closed | On Time
19 | May | DFM Mold | Review DFM Part Drawing and feed back | NW-FOAM SCN-S propose to relax the tolerance | Numworks | Thiti | 2026-05-05 | 2026-05-06 | 2026-05-06 | Close | Closed | On Time
19 | May | PACKING | Support packing | Packing of AMW 03716 MAATEL | Maatel | Thiti | 2026-05-06 | 2026-05-07 | 2026-05-07 | Close | Closed | On Time
19 | May | PACKING | Support packing | Packing of AMW 03718 MAATEL | Maatel | Thiti | 2026-05-06 | 2026-05-07 | 2026-05-07 | Close | Closed | On Time
19 | May | PACKING | Support packing | Packing of AMW 03545 OBC | ณฎฆ | Thiti | 2026-05-07 | 2026-05-08 | 2026-05-08 | Close | Closed | On Time
19 | May | PACKING | Support packing | AMW 03530 SP support sample packing 5 pcs. (shipment) MO: 17125319 | TRACO | Thiti | 2026-05-08 | 2026-05-08 | 2026-05-08 | Close | Closed | On Time
15 | Apr | NPI | NPI Technical support | Design NM-Foam to extend dimension to cover coner of carton | Numworks | Thiti | 2026-04-06 | 2026-04-06 | 2026-04-06 | Close | Closed | On Time
15 | Apr | PACKING | Support packing | AMW-03256-R.BD support packing for shipment | Gutor | Thiti | 2026-04-06 | 2026-04-06 | 2026-04-06 | Close | Closed | On Time
15 | Apr | NPI | NPI Technical support | Kick-Off RFQ project of AMW-QUO944 | MG Development | Thiti | 2026-04-06 | 2026-04-06 | 2026-04-06 | Close | Closed | On Time
15 | Apr | PACKING | Support packing | List up product to shiment within this week |  | Thiti | 2026-04-06 | 2026-04-06 | 2026-04-06 | Close | Closed | On Time
15 | Apr | MEETING | Meeting | MP Quality issue and improvement action for AMW 03457 | Numworks | Thiti | 2026-04-07 | 2026-04-07 | 2026-04-07 | Close | Closed | On Time
15 | Apr | MEETING | Meeting | JRI weekly progress | JRI | Thiti | 2026-04-07 | 2026-04-07 | 2026-04-07 | Close | Closed | On Time
15 | Apr | MEETING | Meeting | Numworks weekly progress | Numworks | Thiti | 2026-04-09 | 2026-04-09 | 2026-04-09 | Close | Closed | On Time
15 | Apr | MEETING | Meeting | JRI support packing to shipment | JRI | Thiti | 2026-04-09 | 2026-04-10 | 2026-04-10 | Close | Closed | On Time
17 | Apr | PACKING | Support packing | AMW 03710 support sample packing 25 pcs. (shipment) MO. 29555101 | ENSTO | Thiti | 2026-04-21 | 2026-04-22 | 2026-04-22 | Close | Closed | On Time
15 | Apr | PACKING | Support packing | AMW 03676 support sample packing (400 pcs) | Leach | Thiti | 2026-04-10 | 2026-04-10 | 2026-04-10 | Close | Closed | On Time
14 | Mar | MEETING | Meeting | Packaging job transfer |  | Kumpon | 2026-03-30 | 2026-03-30 | 2026-03-30 | Close | Closed | On Time
14 | Apr | NPI | NPI Technical support | AMW 03577 Create Label for support attached master carton | Fonroche | Kumpon | 2026-04-01 | 2026-04-02 | 2026-04-02 | Close | Closed | On Time
14 | Apr | RFQ | RFQ | AMW QUO907 confirmation posibility to change Poco pin - Connector to poco pin - Soldering | MG | Bunnarak | 2026-04-03 | 2026-04-03 | 2026-04-03 | Close | Closed | On Time
17 | Apr | PACKING | Design New Packaging | Follow up src wood crate box model 3.5kW to use screw | Enersys | Bunnarak | 2026-04-20 | 2026-04-21 | 2026-04-20 | Close | Closed | On Time
15 | Apr | MEETING | Meeting | JRI weekly progress | JRI | Bunnarak | 2026-04-08 | 2026-04-08 | 2026-04-08 | Close | Closed | On Time
15 | Apr | MEETING | Meeting | Numworks weekly progress | Numworks | Bunnarak | 2026-04-09 | 2026-04-09 | 2026-04-09 | Close | Closed | On Time
15 | Apr | NPI | NPI Technical support | Support cutting pattition for AMW 03577 MP | Fonroche | Nattachai | 2026-04-09 | 2026-04-10 | 2026-04-10 | Close | Closed | On Time
17 | Apr | NPI | NPI Technical support | Support cutting pattition for AMW 03577 MP | Fonroche | Nattachai | 2026-04-20 | 2026-04-20 | 2026-04-20 | Close | Closed | On Time
17 | Apr | PACKING | Support packing | Support packing AMW 03710 | Fonroche | Nattachai | 2026-04-22 | 2026-04-23 | 2026-04-23 | Close | Closed | On Time
17 | Apr | OTHER | Training | Trianing Solidworks |  | Thiti | 2026-04-20 | 2026-04-22 | 2026-04-22 | Close | Closed | On Time
18 | Apr | RFQ | RFQ Packing | AMW QUO949 RFQ Packing | MG Development | Chutiporn | 2026-04-28 | 2026-04-30 | 2026-04-30 | Close | Closed | On Time
18 | Apr | RFQ | RFQ | AMW QUO949 NPI integration requirement | MG Development | Bunnarak | 2026-04-28 | 2026-04-29 | 2026-04-29 | Close | Closed | On Time
17 | Apr | RFQ | RFQ Packing | AMW QUO944 RFQ Packing | MG Development | Bunnarak | 2026-04-23 | 2026-04-24 | 2026-04-24 | Close | Closed | On Time
17 | Apr | RFQ | RFQ | AMW QUO944 NPI integration requirement | MG Development | Bunnarak | 2026-04-23 | 2026-04-24 | 2026-04-04 | Close | Closed | On Time
18 | Apr | RFQ | RFQ Packing | AMW QUO879 RFQ Packing | Actia | Bunnarak | 2026-04-27 | 2026-04-28 | 2026-04-28 | Close | Closed | On Time
18 | Apr | RFQ | RFQ | AMW QUO879 NPI integration requirement | Actia | Bunnarak | 2026-04-27 | 2026-04-28 | 2026-04-27 | Close | Closed | On Time
17 | Apr | Part DFM | Initial review custmer data for DFM | DFM feedback for JRI Nano plug | JRI | Bunnarak | 2026-04-23 | 2026-04-24 | 2026-04-24 | Close | Closed | On Time
17 | Apr | NPI | NPI Technical support | Support adjust shirkwarp machine | Numworks | Bunnarak | 2026-04-22 | 2026-04-23 | 2026-04-23 | Close | Closed | On Time
17 | Apr | PACKING | Support packing | Numworks monitoring production packing with new foam-C (5+3 mm) | Numworks | Chutiporn | 2026-04-23 | 2026-04-24 | 2026-04-24 | Close | Closed | On Time
17 | Apr | PACKING | Support packing | Numworks monitoring production packing with new foam-C (5+3 mm) | Numworks | Thiti | 2026-04-23 | 2026-04-24 | 2026-04-24 | Close | Closed | On Time
17 | Apr | MEETING | Meeting | Kick-off Meeting_Hapticore4 PROTOTYPE_PO# 2613-0554 (per Quotation: AMW-QUO906 Rev02) | Stiwa | Bunnarak | 2026-04-24 | 2026-04-24 | 2026-04-24 | Close | Closed | On Time
19 | May | PACKING | Design New Packaging | Design External packaging for AMW 03317 | IES | Chutiporn | 2026-05-05 | 2026-05-07 | 2026-05-07 | Close | Closed | On Time
19 | May | PACKING | Design New Packaging | Design external packaging for AMW 03317 | IES | Chutiporn | 2026-05-05 | 2026-05-07 | 2026-05-07 | Close | Closed | On Time
20 | May | PACKING | Design New Packaging | Re Design External packaging for AMW03454 OBC | IES | Chutiporn | 2026-05-15 | 2026-05-19 | 2026-05-18 | Close | Closed | On Time
17 | Apr | NPI | NPI Technical support | Review and suggest relax tolerance of NW-Foam Screen | Numworks | Thiti | 2026-04-24 | 2026-04-24 | 2026-04-24 | Close | Closed | On Time
17 | Apr | PACKING | Support packing | Packing of AMW 03189 Viper | Enersys | Thiti | 2026-04-24 | 2026-04-24 | 2026-04-23 | Close | Closed | On Time
17 | Apr | PACKING | Support packing | Packing of AMW 03614 Viper | Enersys | Thiti | 2026-04-23 | 2026-04-23 | 2026-04-23 | Close | Closed | On Time
17 | Apr | PACKING | Support packing | Design Packaging of AMW 03454 OBC | Enersys | Thiti | 2026-04-23 | 2026-04-23 | 2026-04-23 | Close | Closed | On Time
18 | Apr | NPI | NPI Technical support | Trial assembly NW-Batt Adhesive of Delson | Numworks | Thiti | 2026-04-27 | 2026-04-27 | 2026-04-27 | Close | Closed | On Time
18 | Apr | PACKING | Support packing | Take action solution of AMW 03676 LEACH about Packing Drop | Leach | Thiti | 2026-04-27 | 2026-04-27 | 2026-04-27 | Close | Closed | On Time
18 | Apr | PACKING | Support packing | Packing of AMW 03454 OBC | IES | Thiti | 2026-04-27 | 2026-04-27 | 2026-04-27 | Close | Closed | On Time
18 | Apr | PACKING | Support packing | Packing of AMW 03454 OBC | IES | Nattachai | 2026-04-27 | 2026-04-27 | 2026-04-27 | Close | Closed | On Time
18 | Apr | PACKING | Support packing | Confirm NM-Foam C with 10 mm and 5 mm for consume stock | Numworks | Thiti | 2026-04-28 | 2026-04-28 | 2026-04-28 | Close | Closed | On Time
18 | Apr | PACKING | Support packing | Packing of AMW 03369 AEG : 28-Apr | AEG | Thiti | 2026-04-28 | 2026-04-28 | 2026-04-28 | Close | Closed | On Time
18 | Apr | PACKING | Support packing | Packing of AMW 03369 AEG : 28-Apr | AEG | Nattachai | 2026-04-28 | 2026-04-28 | 2026-04-28 | Close | Closed | On Time
18 | Apr | PACKING | Support packing | Packing of AMW 03275 AEG : 28-Apr | AEG | Thiti | 2026-04-28 | 2026-04-28 | 2026-04-28 | Close | Closed | On Time
18 | Apr | PACKING | Support packing | Packing of AMW 03275 AEG : 28-Apr | AEG | Nattachai | 2026-04-28 | 2026-04-28 | 2026-04-28 | Close | Closed | On Time
17 | Apr | NPI | NPI Technical support | Support confirm ID box of master carton numworks | Numworks | Bunnarak | 2026-04-20 | 2026-04-20 | 2026-04-20 | Close | Closed | On Time
17 | Apr | NPI | NPI Technical support | AMW 03577 support cutting partition | Fonroche | Nattachai | 2026-04-21 | 2026-04-21 | 2026-04-21 | Close | Closed | On Time
17 | Apr | PACKING | Support packing | Design packing AMW 03189 Viper | Enersys | Thiti | 2026-04-23 | 2026-04-23 | 2026-04-23 | Close | Closed | On Time
17 | Apr | PACKING | Support packing | Design packing AMW 03614 Viper | Enersys | Thiti | 2026-04-23 | 2026-04-23 | 2026-04-23 | Close | Closed | On Time
18 | Apr | RFQ | RFQ Packing | AMW 03551 - AMW-QUO733 rev06 RFQ Packing | Atlantic | Chutiporn | 2026-04-30 | 2026-05-05 | 2026-05-05 | Close | Closed | On Time
18 | Apr | DFA | Initial review custmer data for DFA | Review Numwork Battery -- alternative source from ZD | Numworks | Thiti | 2026-04-28 | 2026-04-29 | 2026-04-29 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 1st Standalone Internal DFM mold review | Enersys | Bunnarak | 2026-05-11 | 2026-05-11 | 2026-05-11 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 1st Standalone DFM mold meeting | Enersys | Bunnarak | 2026-05-11 | 2026-05-11 | 2026-05-11 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 2nd Standalone Internal DFM mold review | Enersys | Bunnarak | 2026-05-12 | 2026-05-12 | 2026-05-12 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 2nd Standalone DFM mold review | Enersys | Bunnarak | 2026-05-12 | 2026-05-12 | 2026-05-12 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 1st 6bays Internal DFM mold review | Enersys | Bunnarak | 2026-05-13 | 2026-05-13 | 2026-05-13 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 1st 6Bays DFM mold review | Enersys | Bunnarak | 2026-05-13 | 2026-05-13 | 2026-05-13 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 2nd 6Bays Internal DFM mold review | Enersys | Bunnarak | 2026-05-15 | 2026-05-15 | 2026-05-15 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 1st Standalone Internal DFM mold review | Enersys | Thiti | 2026-05-11 | 2026-05-11 | 2026-05-11 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 1st Standalone DFM mold meeting | Enersys | Thiti | 2026-05-11 | 2026-05-11 | 2026-05-11 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 2nd Standalone Internal DFM mold review | Enersys | Thiti | 2026-05-12 | 2026-05-12 | 2026-05-12 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 2nd Standalone DFM mold review | Enersys | Thiti | 2026-05-12 | 2026-05-12 | 2026-05-12 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 1st 6bays Internal DFM mold review | Enersys | Thiti | 2026-05-13 | 2026-05-13 | 2026-05-13 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 1st 6Bays DFM mold review | Enersys | Thiti | 2026-05-13 | 2026-05-13 | 2026-05-13 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 1st Standalone Internal DFM mold review | Enersys | Tae | 2026-05-11 | 2026-05-11 | 2026-05-11 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 1st Standalone DFM mold meeting | Enersys | Tae | 2026-05-11 | 2026-05-11 | 2026-05-11 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 2nd Standalone Internal DFM mold review | Enersys | Tae | 2026-05-12 | 2026-05-12 | 2026-05-12 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 2nd Standalone DFM mold meeting | Enersys | Tae | 2026-05-12 | 2026-05-12 | 2026-05-12 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 2nd Standalone Internal DFM mold review | Enersys | Tae | 2026-05-12 | 2026-05-12 | 2026-05-12 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 1st 6bays Internal DFM mold review | Enersys | Tae | 2026-05-13 | 2026-05-13 | 2026-05-13 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 1st 6bays DFM mold meeting | Enersys | Tae | 2026-05-13 | 2026-05-13 | 2026-05-13 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM Part Drawing and feed back | Review steel bar DFM part for localization | Gutor | Tae | 2026-05-14 | 2026-05-15 | 2026-05-15 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM Part Drawing and feed back | Review Heatsink DFM part for localization | Gutor | Tae | 2026-05-14 | 2026-05-15 | 2026-05-15 | Close | Closed | On Time
20 | May | DFM Mold | Review DFM MOLD and feed back | 2nd 6Bays Internal DFM mold review | Enersys | Tae | 2026-05-15 | 2026-05-15 | 2026-05-15 | Close | Closed | On Time
21 | May | DFM Mold | Review DFM MOLD and feed back | 2nd 6Bays Internal DFM mold meeting | Enersys | Tae | 2026-05-18 | 2026-05-18 | 2026-05-18 | Close | Closed | On Time
20 | May | RFQ | RFQ Packing | AMW QUO958 Rev01 | MG Development | Chutiporn | 2026-05-11 | 2026-05-13 | 2026-05-13 | Close | Closed | On Time
20 | May | RFQ | RFQ Packing | AMW-QUO957 Rev01.01 RFQ Packing | Digital Power Systems | Chutiporn | 2026-05-12 | 2026-05-14 | 2026-05-14 | Close | Closed | On Time
20 | May | PACKING | Design New Packaging | AMW 03545-OBC Elips720 for IES_Redesign of Packing Concept | IES | Chutiporn | 2026-05-13 | 2026-05-15 | 2026-05-15 | Close | Closed | On Time
21 | May | NPI | NPI Technical support | Support customer STIWA | Stiwa | Bunnarak | 2026-05-19 | 2026-05-21 | 2026-05-21 | Close | Closed | On Time
21 | May | DFM Mold | Review DFM MOLD and feed back | Review the new proposal of project updated and timeline for the stand alone project. | Enersys | Bunnarak | 2026-05-21 | 2026-05-21 | 2026-05-21 | Close | Closed | On Time
21 | May | MEETING | Meeting | AMW QUO961 EMERSON project alignment | Emerson | Bunnarak | 2026-05-22 | 2026-05-22 | 2026-05-22 | Close | Closed | On Time
21 | May | DFM Mold | Review DFM MOLD and feed back | 2nd 6Bays Internal DFM mold meeting | Enersys | Thiti | 2026-05-18 | 2026-05-18 | 2026-05-18 | Close | Closed | On Time
21 | May | MEETING | Meeting | JRI weekly meeting | JRI | Thiti | 2026-05-18 | 2026-05-18 | 2026-05-18 | Close | Closed | On Time
21 | May | DFM Mold | DFM Feedback to Customer and waiting customer review | Plastic for JRI Nano Plug QUO874 | JRI | Thiti | 2026-05-18 | 2026-05-19 | 2026-05-19 | Close | Closed | On Time
21 | May | PACKING | Support packing | Packaging Design of AMW 03207 BOARD VIPER | Enersys | Thiti | 2026-05-18 | 2026-05-19 | 2026-05-19 | Close | Closed | On Time
21 | May | PACKING | Support packing | Packaging Design of AMW 03661 AEG | AEG | Thiti | 2026-05-18 | 2026-05-19 | 2026-05-19 | Close | Closed | On Time
21 | May | PACKING | Support packing | Packing of AMW 03520 FONROCHE ( Repacking ) | Fonroche | Thiti | 2026-05-20 | 2026-05-20 | 2026-05-20 | Close | Closed | On Time
21 | May | PACKING | Support packing | Packing of AMW 03521 FONROCHE ( Repacking ) | Fonroche | Thiti | 2026-05-20 | 2026-05-20 | 2026-05-20 | Close | Closed | On Time
21 | May | PACKING | Support packing | Packing of AMW 03207 BOARD VIPER | Enersys | Thiti | 2026-05-20 | 2026-05-20 | 2026-05-20 | Close | Closed | On Time
21 | May | NPI | NPI Technical support | Confirm NW-Reset Silicone with NEW grey color | Numworks | Thiti | 2026-05-20 | 2026-05-20 | 2026-05-20 | Close | Closed | On Time
21 | May | PACKING | Support packing | Packing of AMW 03685 AEG | AEG | Thiti | 2026-05-21 | 2026-05-21 | 2026-05-21 | Close | Closed | On Time
21 | May | PACKING | Support packing | Packing of AMW 03661 AEG | AEG | Thiti | 2026-05-21 | 2026-05-21 | 2026-05-21 | Close | Closed | On Time
21 | May | PACKING | Support packing | Packing of AMW 03371 AEG | AEG | Thiti | 2026-05-21 | 2026-05-21 | 2026-05-21 | Close | Closed | On Time
21 | May | DFM Mold | Review DFM MOLD and feed back | Review the new proposal of project updated and timeline for the stand alone project. | Enersys | Thiti | 2026-05-21 | 2026-05-21 | 2026-05-21 | Close | Closed | On Time
21 | May | PROJECT | KAIZEN | Kaizen JIG attached Foam screen NW | Numworks | Thiti | 2026-05-20 | 2026-05-21 | 2026-05-21 | Close | Closed | On Time
21 | May | PACKING | Support packing | Packing of AMW 03275 AEG | AEG | Thiti | 2026-05-22 | 2026-05-22 | 2026-05-22 | Close | Closed | On Time
21 | May | PACKING | Support packing | Packing of AMW 03675 LEACH | Leach | Thiti | 2026-05-22 | 2026-05-22 | 2026-05-22 | Close | Closed | On Time
21 | May | DFM Mold | DFM Feedback to Customer and waiting customer review | GUTOR Localization (Heat Sink) Drawing comparison between Readore and Customer | Gutor | Tae | 2026-05-18 | 2026-05-19 | 2026-05-19 | Close | Closed | On Time
21 | May | DFM Mold | DFM Feedback to Customer and waiting customer review | Metal for JRI Nano plug | JRI | Tae | 2026-05-18 | 2026-05-19 | 2026-05-19 | Close | Closed | On Time
21 | May | DFM Mold | DFM Feedback to Customer and waiting customer review | GUTOR (Heat Sink) Drawing comparison between New Propose 16 FIN & 851-9876 Rev.02 | Gutor | Tae | 2026-05-19 | 2026-05-20 | 2026-05-20 | Close | Closed | On Time
21 | May | PACKING | Prepare customer label | Prepare Label AMW 03739 AUX Board GL0023748-0000-3.2 | Enersys | Tae | 2026-05-20 | 2026-05-21 | 2026-05-20 | Close | Closed | On Time
21 | May | PACKING | Prepare customer label | Prepare Label AMW 03206-01-13.5 Backplane GL0014718-0001-13.5 | Enersys | Tae | 2026-05-20 | 2026-05-21 | 2026-05-20 | Close | Closed | On Time
21 | May | PACKING | Prepare customer label | Prepare Label AMW 03209-01-13.5 EMC GL0016316-0001-13.5 | Enersys | Tae | 2026-05-20 | 2026-05-21 | 2026-05-20 | Close | Closed | On Time
21 | May | DFM Mold | Review DFM MOLD and feed back | Review the new proposal of project updated and timeline for the stand alone project. | Enersys | Tae | 2026-05-21 | 2026-05-21 | 2026-05-21 | Close | Closed | On Time
21 | May | PACKING | Prepare customer label | Prepare Label AMW 03156-00-13.8 Control Board GL0013339-0000-13.8 | Enersys | Tae | 2026-05-21 | 2026-05-22 | 2026-05-20 | Close | Closed | On Time
21 | May | PACKING | Prepare customer label | Prepare Label AMW 03157-02-13.7 Power Board GL0013336-0002-13.7 | Enersys | Tae | 2026-05-21 | 2026-05-22 | 2026-05-20 | Close | Closed | On Time
21 | May | PACKING | Prepare customer label | Prepare Label AMW 03208-00-8.4 GL0015848-0000 DISPLAY BOARD ENTRY | Enersys | Tae | 2026-05-21 | 2026-05-22 | 2026-05-20 | Close | Closed | On Time
21 | May | PACKING | Prepare customer label | Label AMW 03577 | Fonroche | Tae | 2026-05-22 | 2026-05-25 | 2026-05-25 | Close | Closed | On Time
21 | May | PACKING | Prepare customer label | Label AMW 03746 | JRI | Tae | 2026-05-22 | 2026-05-25 | 2026-05-25 | Close | Closed | On Time
21 | May | PACKING | Prepare customer label | Label AMW 03668 | JRI | Tae | 2026-05-22 | 2026-05-25 | 2026-05-25 | Close | Closed | On Time
22 | May | NPI | Trial tooling | Visit for technical confirmation |  | Tae | 2026-05-25 | 2026-05-25 | 2026-05-25 | Close | Closed | On Time
22 | May | Part DFM | Review internal DFM | Confirm Heat sink quotation_DONGGUAN READORE | Gutor | Tae | 2026-05-25 | 2026-05-26 | 2026-05-26 | Close | Closed | On Time
22 | May | Part DFM | Review internal DFM | GUTOR Localization and Cost reduction timeline (Metal bar) | Gutor | Tae | 2026-05-25 | 2026-05-26 | 2026-05-26 | Close | Closed | On Time
22 | May | DFM Mold | Review DFM MOLD and feed back | Follow up DFM Viper Stand-alone & 6 Bays | Enersys | Tae | 2026-05-27 | 2026-05-27 | 2026-05-27 | Close | Closed | On Time
22 | May | DFM Mold | Review DFM MOLD and feed back | DFM Mold metal part of standalond | Enersys | Tae | 2026-05-28 | 2026-05-29 | 2026-05-29 | Close | Closed | On Time
22 | May | OTHER | Training | barTender print training |  | Tae | 2026-05-28 | 2026-05-28 | 2026-05-28 | Close | Closed | On Time
22 | May | PACKING | Prepare customer label | Prepare label AMW 03156 (Revise digit follow customer request) | Enersys | Tae | 2026-05-28 | 2026-05-29 | 2026-05-28 | Close | Closed | On Time
22 | May | PACKING | Prepare customer label | Prepare label AMW 03209 (Revise digit follow customer request) | Enersys | Tae | 2026-05-28 | 2026-05-29 | 2026-05-28 | Close | Closed | On Time
21 | May | PACKING | Design New Packaging | Discuss OBC packing | IES | Chutiporn | 2026-05-21 | 2026-05-21 | 2026-05-21 | Close | Closed | On Time
21 | May | PACKING | Design New Packaging | Technical support for confirm PaperPad subtitute for MP AMW 03100 |  | Chutiporn | 2026-05-21 | 2026-05-21 | 2026-05-21 | Close | Closed | On Time
21 | May | RFQ | RFQ Packing | AMW QUO889 Rev2.01 Packing RFQ | Leach | Chutiporn | 2026-05-21 | 2026-05-22 | 2026-05-22 | Close | Closed | On Time
21 | May | MEETING | Meeting | AMW QUO961 EMERSON project alignment | Emerson | Chutiporn | 2026-05-22 | 2026-05-22 | 2026-05-22 | Close | Closed | On Time
21 | May | RFQ | RFQ Packing | [REQ] New Tray for Magnetic Parts (Stiwa) | Stiwa | Chutiporn | 2026-05-22 | 2026-05-22 | 2026-05-22 | Close | Closed | On Time
21 | May | PACKING | Design New Packaging | AMW 03617-01-02 design packing concept | Enersys | Chutiporn | 2026-05-22 | 2026-05-25 | 2026-05-25 | Close | Closed | On Time
22 | May | RFQ | RFQ Packing | AMW QUO961 (5 Box Build/20 PCBA) RFQ Packing | Emersob | Chutiporn | 2026-05-25 | 2026-05-27 | 2026-05-27 | Close | Closed | On Time
22 | May | NPI | Trial tooling | Visit for technical confirmation Fagerdala |  | Chutiporn | 2026-05-26 | 2026-05-26 | 2026-05-26 | Close | Closed | On Time
22 | May | PACKING | Confirm packing | Support confirm est. net and gross weight of Kit Option 3BAY - AMW 03617 | Enersys | Chutiporn | 2026-05-26 | 2026-05-26 | 2026-05-26 | Close | Closed | On Time
23 | Jun | RFQ | RFQ Packing | AMW-QUO969 (5 PCBA) RFQ Packing | Staubli Hangzhou | Chutiporn | 2026-06-03 | 2026-06-05 | 2026-06-04 | Close | Closed | On Time
22 | May | PACKING | Design New Packaging | Confirm tray plug nano | JRI | Chutiporn | 2026-05-28 | 2026-05-29 | 2026-05-28 | Close | Closed | On Time
22 | May | RFQ | RFQ Packing | AMW-QUO924 (1 PCBA) RFQ packing | Gutor | Chutiporn | 2026-05-29 | 2026-06-02 | 2026-05-29 | Close | Closed | On Time
23 | Jun | RFQ | RFQ Packing | AMW-QUO967 (3 PCBA) | EMSISO | Chutiporn | 2026-06-04 | 2026-06-08 | 2026-06-04 | Close | Closed | On Time
22 | May | Part DFM | Initial review custmer data for DFM | DFM Part of new project from traco (Not have RFQ) | Traco | Thiti | 2026-05-26 | 2026-05-27 | 2026-05-27 | Close | Closed | On Time
22 | May | PACKING | Support packing | Packing of AMW 03530 TRACO | Traco | Thiti | 2026-05-27 | 2026-05-27 | 2026-05-27 | Close | Closed | On Time
22 | May | PACKING | Support packing | Packing of AMW 03531 TRACO | Traco | Thiti | 2026-05-28 | 2026-05-29 | 2026-05-29 | Close | Closed | On Time
22 | May | PACKING | Support packing | Packing of AMW 03533 TRACO | Traco | Thiti | 2026-05-27 | 2026-05-27 | 2026-05-27 | Close | Closed | On Time
22 | May | PACKING | Support packing | Packing of AMW 03534 TRACO | Traco | Thiti | 2026-05-27 | 2026-05-27 | 2026-05-27 | Close | Closed | On Time
22 | May | DFM Mold | Review DFM MOLD and feed back | Follow up DFM Viper Stand-alone & 6 Bays | Enersys | Thiti | 2026-05-27 | 2026-05-27 | 2026-05-27 | Close | Closed | On Time
22 | May | DFM Mold | Review DFM MOLD and feed back | DFM meeting for overmold of JRI | JRI | Thiti | 2026-05-28 | 2026-05-28 | 2026-05-28 | Close | Closed | On Time
23 | Jun | PACKING | Support packing | Packing of AMW 02517 SLAT | SLAT | Thiti | 2026-06-04 | 2026-06-05 | 2026-06-05 | Close | Closed | On Time
23 | Jun | PACKING | Support packing | Packing sample AMW 03667/JRI | JRI | Thiti | 2026-06-04 | 2026-06-04 | 2026-06-04 | Close | Closed | On Time
23 | Jun | NPI | Trial tooling | JRI GDS Project go to supplier for DFM mold and confirm assessory need for injection machine | JRI | Thiti | 2026-06-04 | 2026-06-04 | 2026-06-04 | Close | Closed | On Time
23 | Jun | PACKING | Support packing | AMW 03457 SP/NUMWORK support packing | Numworks | Thiti | 2026-06-05 | 2026-06-05 | 2026-06-05 | Close | Closed | On Time
23 | Jun | PACKING | Support packing | AMW 03739 PCB/VIPER support packing | Enersys | Thiti | 2026-06-05 | 2026-06-05 | 2026-06-05 | Close | Closed | On Time
23 | Jun | DFM Mold | Review DFM MOLD and feed back | Confirm DFM mold JRI overmold green digital | JRI | Thiti | 2026-06-05 | 2026-06-05 | 2026-06-05 | Close | Closed | On Time
24 | Jun | PACKING | Support packing | Packing of AMW 03626 IES | IES | Chutiporn | 2026-06-12 | 2026-06-12 | 2026-06-12 | Close | Closed | On Time
24 | Jun | PACKING | Support packing | Packing of AMW 03724 SEFAM | SEFAM | Chutiporn | 2026-06-12 | 2026-06-12 | 2026-06-12 | Close | Closed | On Time
24 | Jun | NPI | NPI Technical support | Injection Machine ETA AMW wk22. | JRI | Thiti | 2026-06-08 | 2026-06-09 | 2026-06-08 | Close | Closed | On Time
22 | May | PACKING | Design New Packaging | Review technical data of NW SP10 individual box and ship boxwith Customer and supplier | Numworks | Bunnarak | 2026-05-26 | 2026-05-26 | 2026-05-26 | Close | Closed | On Time
22 | May | DFM Mold | Review DFM MOLD and feed back | Follow up DFM Viper Stand-alone & 6 Bays | Enersys | Bunnarak | 2026-05-27 | 2026-05-27 | 2026-05-27 | Close | Closed | On Time
22 | May | DFM Mold | Review DFM MOLD and feed back | DFM meeting for overmold of JRI | JRI | Bunnarak | 2026-05-28 | 2026-05-28 | 2026-05-28 | Close | Closed | On Time
22 | May | PACKING | Confirm packing | Confirm SP10 all box | Numworks | Bunnarak | 2026-05-28 | 2026-05-29 | 2026-05-29 | Close | Closed | On Time
22 | May | MEETING | Meeting | Numworks weekly meeting | Numworks | Bunnarak | 2026-05-28 | 2026-05-28 | 2026-05-28 | Close | Closed | On Time
22 | May | MEETING | Meeting | Numworks weekly meeting | Numworks | Bunnarak | 2026-05-28 | 2026-05-28 | 2026-05-28 | Close | Closed | On Time
23 | Jun | NPI | NPI Technical support | Analysis Viper problem about WIMA with team | Enersys | Thiti | 2026-06-02 | 2026-06-04 | 2026-06-04 | Close | Closed | On Time
23 | Jun | NPI | NPI Technical support | Analysis Viper problem about WIMA with team | Enersys | Bunnarak | 2026-06-02 | 2026-06-04 | 2026-06-04 | Close | Closed | On Time
23 | Jun | NPI | NPI Technical support | Analysis Viper problem about WIMA with team | Enersys | Tae | 2026-06-02 | 2026-06-04 | 2026-06-04 | Close | Closed | On Time
22 | May | PACKING | Design New Packaging | Withdraw the plastic bag from the stock without returning. |  | Chutiporn | 2026-05-28 | 2026-05-28 | 2026-05-28 | Close | Closed | On Time
22 | May | PACKING | Design New Packaging | request Box Compression Test of AMW Carton |  | Chutiporn | 2026-05-29 | 2026-05-29 | 2026-05-29 | Close | Closed | On Time
23 | Jun | PACKING | Design New Packaging | PARTITION_QUO733 Atlantic - Updated Drawing | Atlantic | Chutiporn | 2026-06-03 | 2026-06-04 | 2026-06-04 | Close | Closed | On Time
23 | Jun | PACKING | Design New Packaging | PARTITION_QUO924 - Updated Drawing |  | Chutiporn | 2026-06-03 | 2026-06-04 | 2026-06-04 | Close | Closed | On Time
23 | Jun | PACKING | Design New Packaging | COnfirm OBC sample box | IES | Chutiporn | 2026-06-03 | 2026-06-04 | 2026-06-03 | Close | Closed | On Time
23 | Jun | PACKING | Design New Packaging | Packing Concept of AMW03540-44_SLAT - Updated |  | Chutiporn | 2026-06-04 | 2026-06-05 | 2026-06-05 | Close | Closed | On Time
23 | Jun | PACKING | Design New Packaging | AMW-QUO606 Rev.06.02 : Update packaging assy confirm partition and inform problem to supplier | IES | Chutiporn | 2026-06-04 | 2026-06-05 | 2026-06-05 | Close | Closed | On Time
23 | Jun | RFQ | RFQ Packing | AMW-QUO889 Rev01.01 confirm RFQ packing | Leach | Chutiporn | 2026-06-05 | 2026-06-08 | 2026-06-05 | Close | Closed | On Time
23 | Jun | DFA | Initial review custmer data for DFA | DFA viper standalone after customer update 3D part |  | Tae | 2026-06-03 | 2026-06-09 | 2026-06-09 | Close | Closed | On Time
23 | Jun | MEETING | Meeting | JRI weekly meeting | JRI | Bunnarak | 2026-06-01 | 2026-06-01 | 2026-06-01 | Close | Closed | On Time
23 | Jun | DFA | DFA Feedback to Customer and waiting customer review | Viper standalone clearance check | Enersys | Bunnarak | 2026-06-04 | 2026-06-08 | 2026-06-08 | Close | Closed | On Time
23 | Jun | MEETING | Meeting | Numworks weekly meeting | Numworks | Bunnarak | 2026-06-04 | 2026-06-04 | 2026-06-04 | Close | Closed | On Time
23 | Jun | PACKING | Design New Packaging | Confirm design Tray AMW 03675 | Leach | Bunnarak | 2026-06-05 | 2026-06-05 | 2026-06-05 | Close | Closed | On Time
23 | Jun | PACKING | Design New Packaging | Weigth packing sample of SP10 | Numworks | Bunnarak | 2026-06-05 | 2026-06-05 | 2026-06-05 | Close | Closed | On Time
24 | Jun | PACKING | Design New Packaging | Update packaging by remove ESD bag and Tie/AMW 03551 - AMW-QUO733 | Atlantic | Chutiporn | 2026-06-08 | 2026-06-09 | 2026-06-08 | Close | Closed | On Time
24 | Jun | PACKING | Design New Packaging | ESD COVER_AMW QUO889 - Alternative Materials |  | Chutiporn | 2026-06-08 | 2026-06-08 | 2026-06-08 | Close | Closed | On Time
24 | Jun | RFQ | RFQ Packing | AMW-QUO972 Rev01.01 for Gutor RFQ packing | GUTOR | Chutiporn | 2026-06-08 | 2026-06-10 | 2026-06-08 | Close | Closed | On Time
24 | Jun | PACKING | Support packing | AMW 03676 LEACH support packing | Leach | Chutiporn | 2026-06-10 | 2026-06-10 | 2026-06-10 | Close | Closed | On Time
24 | Jun | PACKING | Support packing | AMW 03530 SP TRACO support packing | Traco | Chutiporn | 2026-06-11 | 2026-06-12 | 2026-06-12 | Close | Closed | On Time
25 | Jun | PACKING | Support packing | AMW 03531 SP TRACO support packing | Traco | Chutiporn | 2026-06-19 | 2026-06-19 | 2026-06-19 | Close | Closed | On Time
25 | Jun | PACKING | Support packing | AMW 03533 SP TRACO support packing | Traco | Chutiporn | 2026-06-19 | 2026-06-19 | 2026-06-19 | Close | Closed | On Time
24 | Jun | PACKING | Support packing | AMW 03534 SP TRACO support packing | Traco | Chutiporn | 2026-06-11 | 2026-06-12 | 2026-06-12 | Close | Closed | On Time
24 | Jun | NPI | NPI Technical support | Discuss about the measurement concept Straingauge with supplier | Enersys | Tae | 2026-06-09 | 2026-06-09 | 2026-06-09 | Close | Closed | On Time
24 | Jun | NPI | NPI Technical support | Discuss about the measurement concept Straingauge with supplier | Enersys | Thiti | 2026-06-09 | 2026-06-09 | 2026-06-09 | Close | Closed | On Time
24 | Jun | NPI | NPI Technical support | Support assy New NW-Batt Adhesive and pull test | Numworks | Thiti | 2026-06-08 | 2026-06-08 | 2026-06-08 | Close | Closed | On Time
24 | Jun | PACKING | Prepare customer label | AMW 03511 update Label detail | IES | Tae | 2026-06-08 | 2026-06-09 | 2026-06-08 | Close | Closed | On Time
24 | Jun | PACKING | Prepare customer label | AMW 03545 update Label detail | IES | Tae | 2026-06-08 | 2026-06-09 | 2026-06-08 | Close | Closed | On Time
24 | Jun | OTHER | Training | Training solidworks Assembly |  | Bunnarak | 2026-06-09 | 2026-06-10 | 2026-06-10 | Close | Closed | On Time
24 | Jun | MEETING | Meeting | AMW-QUO957 Rev 02.01 - HDS20 Power Supply Unit for DPS |  | Bunnarak | 2026-06-10 | 2026-06-11 | 2026-06-11 | Close | Closed | On Time
24 | Jun | PACKING | Confirm packing | COnfirm assembly Mastercarton box with foam 10 mm | Numworks | Bunnarak | 2026-06-11 | 2026-06-12 | 2026-06-12 | Close | Closed | On Time
24 | Jun | PACKING | Support packing | Support packing NW SP10 to drop test | Numworks | Bunnarak | 2026-06-12 | 2026-06-12 | 2026-06-12 | Close | Closed | On Time
24 | Jun | DFM Mold | Review DFM MOLD and feed back | Review DFM Viper Standalone of Sirikomol | Enersys | Thiti | 2026-06-09 | 2026-06-09 | 2026-06-09 | Close | Closed | On Time
24 | Jun | DFM Mold | Review DFM MOLD and feed back | Review DFM Viper Standalone of Sirikomol | Enersys | Tae | 2026-06-09 | 2026-06-09 | 2026-06-09 | Close | Closed | On Time
24 | Jun | DFM Mold | Review DFM MOLD and feed back | (Tentative) Viper Standalone DFM meeting w/Sirikomol | Enersys | Thiti | 2026-06-09 | 2026-06-09 | 2026-06-09 | Close | Closed | On Time
24 | Jun | DFM Mold | Review DFM MOLD and feed back | (Tentative) Viper Standalone DFM meeting w/Sirikomol | Enersys | Tae | 2026-06-09 | 2026-06-09 | 2026-06-09 | Close | Closed | On Time
24 | Jun | MEETING | meeting | Numworks weekly meeting | Numworks | Thiti | 2026-06-11 | 2026-06-11 | 2026-06-11 | Close | Closed | On Time
24 | Jun | RFQ | RFQ Packing | AMW QUO968 Enersys Cable charger GL0024410-0000 | Enersys | Chutiporn | 2026-06-09 | 2026-06-11 | 2026-06-11 | Close | Closed | On Time
24 | Jun | PACKING | Confirm packing | Withdraw the plastic bag from the stock without returning |  | Chutiporn | 2026-06-11 | 2026-06-11 | 2026-06-11 | Close | Closed | On Time
24 | Jun | PACKING | Design New Packaging | AMW 03545-OBC Elips720 for IES_Redesign of Packing Concept | IES | Chutiporn | 2026-06-12 | 2026-06-12 | 2026-06-12 | Close | Closed | On Time
24 | Jun | DFM Mold | Review DFM MOLD and feed back | GUTOR Localization NPI Integration Metal part DFM | GUTOR | Tae | 2026-06-11 | 2026-06-12 | 2026-06-11 | Close | Closed | On Time
24 | Jun | DFM Mold | Review DFM MOLD and feed back | NPI Integration Metal part DFM Heatsink READORE | GUTOR | Tae | 2026-06-09 | 2026-06-10 | 2026-06-10 | Close | Closed | On Time
24 | Jun | Part DFM | Initial review custmer data for DFM | DFM plastic parts of new product TRACO new model | TRACO | Thiti | 2026-06-11 | 2026-06-12 | 2026-06-12 | Close | Closed | On Time
24 | Jun | PACKING | Design New Packaging | Update packaging Packing Concept of AMW 03743 for STIWA | Stiwa | Chutiporn | 2026-06-09 | 2026-06-10 | 2026-06-09 | Close | Closed | On Time
24 | Jun | PACKING | Prepare customer label | AMW03486 edit label template | FONROCHE | Tae | 2026-06-10 | 2026-06-11 | 2026-06-11 | Close | Closed | On Time
24 | Jun | PACKING | Prepare customer label | AMW03100 edit label template | MAATEL | Tae | 2026-06-10 | 2026-06-11 | 2026-06-11 | Close | Closed | On Time
24 | Jun | PACKING | Prepare customer label | AMW03520-1 edit label template | FONROCHE | Tae | 2026-06-10 | 2026-06-11 | 2026-06-11 | Close | Closed | On Time
24 | Jun | PACKING | Prepare customer label | AMW 03521-1 edit label template | FONROCHE | Tae | 2026-06-10 | 2026-06-11 | 2026-06-11 | Close | Closed | On Time
24 | Jun | NPI | NPI Technical support | Tape test label for JRI green digital sensor | JRI | Tae | 2026-06-12 | 2026-06-12 | 2026-06-12 | Close | Closed | On Time
25 | Jun | RFQ | RFQ Packing | AMW-QUO957(BoxBuild+PCBA) RFQ packing | Digital power systems | Chutiporn | 2026-06-16 | 2026-06-17 | 2026-06-09 | Close | Closed | On Time
25 | Jun | PACKING | Confirm packing | Confirm Retail foam c 5 mm for support stack 5 layer | Numworks | Chutiporn | 2026-06-16 | 2026-06-16 | 2026-06-16 | Close | Closed | On Time
25 | Jun | PACKING | Confirm packing | Make record document packing part (N' After) |  | Chutiporn | 2026-06-15 | 2026-06-18 | 2026-06-18 | Close | Closed | On Time
25 | Jun | RFQ | RFQ Packing | AMW-QUO975 (BoxBuild+PCBA) RFQ oacking | my-PV | Chutiporn | 2026-06-16 | 2026-06-17 | 2026-06-17 | Close | Closed | On Time
25 | Jun | PACKING | Confirm packing | Confirm Tray ESD TRAY AMW 03721 Plug nano | JRI | Chutiporn | 2026-06-18 | 2026-06-19 | 2026-06-19 | Close | Closed | On Time
25 | Jun | PACKING | Support packing | Packing of AMW 02517 | SLAT | Chutiporn | 2026-06-19 | 2026-06-19 | 2026-06-19 | Close | Closed | On Time
25 | Jun | MEETING | Meeting | AMW 03617-00-01 Kick off meeting | Enersys | Chutiporn | 2026-06-19 | 2026-06-19 | 2026-06-19 | Close | Closed | On Time
25 | Jun | MEETING | Meeting | JRI Weekly meeting | JRI | Tae | 2026-06-15 | 2026-06-15 | 2026-06-15 | Close | Closed | On Time
25 | Jun | PACKING | Prepare customer label | AMW03577 prepare label template | FONROCHE | Tae | 2026-06-15 | 2026-06-16 | 2026-06-16 | Close | Closed | On Time
25 | Jun | PACKING | Prepare customer label | AMW03519 prepare lable template | FONROCHE | Tae | 2026-06-15 | 2026-06-16 | 2026-06-16 | Close | Closed | On Time
25 | Jun | NPI | NPI Technical support | Create drawing Sheet Metal / Plastics Quote |  | Tae | 2026-06-17 | 2026-06-18 | 2026-06-18 | Close | Closed | On Time
25 | Jun | OTHER | Visit Exhibition | Visit Manufacturing process exhibition |  | Tae | 2026-06-18 | 2026-06-18 | 2026-06-18 | Close | Closed | On Time
25 | Jun | DFM Mold | Review DFM MOLD and feed back | Confirm Readore 3D drwing of heatsink | GUTOR | Tae | 2026-06-18 | 2026-06-19 | 2026-06-19 | Close | Closed | On Time
25 | Jun | MEETING | Meeting | JRI Weekly meeting | JRI | Bunnarak | 2026-06-15 | 2026-06-15 | 2026-06-15 | Close | Closed | On Time
25 | Jun | DFA | DFA Feedback to Customer and waiting customer review | Viper 6 bays clearance checking | Enersys | Bunnarak | 2026-06-16 | 2026-06-18 | 2026-06-18 | Close | Closed | On Time
25 | Jun | NPI | NPI Technical support | Technical support drop test information question from prg. | Numworks | Bunnarak | 2026-06-17 | 2026-06-17 | 2026-06-17 | Close | Closed | On Time
25 | Jun | NPI | NPI Technical support | Module GUTOR damaged meeting | GUTOR | Bunnarak | 2026-06-18 | 2026-06-18 | 2026-06-18 | Close | Closed | On Time
25 | Jun | OTHER | Visit Exhibition | Visit Manufacturing process exhibition |  | Bunnarak | 2026-06-19 | 2026-06-19 | 2026-06-19 | Close | Closed | On Time
25 | Jun | MEETING | Meeting | JRI Weekly meeting | JRI | Thiti | 2026-06-15 | 2026-06-15 | 2026-06-15 | Close | Closed | On Time
25 | Jun | PACKING | Support packing | Make WI to training team for handmade JRI AMW 03668 | JRI | Thiti | 2026-06-15 | 2026-06-15 | 2026-06-15 | Close | Closed | On Time
25 | Jun | PACKING | Support packing | Make WI to training team for handmade JRI AMW 03669 | JRI | Thiti | 2026-06-15 | 2026-06-15 | 2026-06-15 | Close | Closed | On Time
25 | Jun | NPI | NPI Technical support | Clarify the correct product structure of JRI AMW 03669, AMW 03670 and request revise Drawing and BOM | JRI | Thiti | 2026-06-16 | 2026-06-16 | 2026-06-16 | Close | Closed | On Time
25 | Jun | NPI | Sample assembly Support | Make Handmade part for JRI overmolding | JRI | Thiti | 2026-06-15 | 2026-06-19 | 2026-06-19 | Close | Closed | On Time
25 | Jun | OTHER | Visit Exhibition | Visit Manufacturing process exhibition |  | Thiti | 2026-06-17 | 2026-06-17 | 2026-06-17 | Close | Closed | On Time
25 | Jun | DFM Mold | Review DFM MOLD and feed back | Follow up DFM Viper Stand-alone meeting with customer | Enersys | Thiti | 2026-06-18 | 2026-06-18 | 2026-06-18 | Close | Closed | On Time
25 | Jun | Part DFM | Review internal DFM | Traco Power new product DFM part | Traco | Thiti | 2026-06-18 | 2026-06-19 | 2026-06-19 | Close | Closed | On Time
25 | Jun | MEETING | Meeting | AMW 03617-00-01 Kick off meeting | Enersys | Thiti | 2026-06-19 | 2026-06-19 | 2026-06-19 | Close | Closed | On Time
25 | Jun | PROJECT | KAIZEN | Prepare KAIZEN report |  | Thiti | 2026-06-19 | 2026-06-19 | 2026-06-19 | Close | Closed | On Time
26 | Jun | PACKING | Confirm packing | Artwork proof for individule box Retail and SchoolProperties Numworks | Numworks | Chutiporn | 2026-06-22 | 2026-06-23 | 2026-06-23 | Close | Closed | On Time
26 | Jun | RFQ | RFQ Packing | AMW QUO976 RFQ packing design | Enersys | Chutiporn | 2026-06-22 | 2026-06-23 | 2026-06-17 | Close | Closed | On Time
26 | Jun | MEETING | Meeting | Kick-Off New Project AMW 03767 | Bernina | Chutiporn | 2026-06-24 | 2026-06-24 | 2026-06-24 | Close | Closed | On Time
26 | Jun | MEETING | Meeting | Kick-Off New Project AMW 03767 | Bernina | Tae | 2026-06-24 | 2026-06-24 | 2026-06-24 | Close | Closed | On Time
26 | Jun | PACKING | Confirm packing | AMW 03511 – Packing Design Issue / Container Loading | IES | Chutiporn | 2026-06-24 | 2026-06-25 | 2026-06-25 | Close | Closed | On Time
26 | Jun | PACKING | Confirm packing | Confirm tray for product AMW 03754, AMW 03755 | JRI | Chutiporn | 2026-06-25 | 2026-06-26 | 2026-06-26 | Close | Closed | On Time
26 | Jun | PACKING | Support packing | AMW 03743 STIWA support packing | Stiwa | Chutiporn | 2026-06-25 | 2026-06-26 | 2026-06-25 | Close | Closed | On Time
26 | Jun | MEETING | Meeting | JRI weekly project review | JRI | Thiti | 2026-06-22 | 2026-06-22 | 2026-06-22 | Close | Closed | On Time
26 | Jun |  |  | Follow up TRI-BESTECH: AMW - INJECTION MOLDING MACHINE | JRI | Thiti | 2026-06-23 | 2026-06-24 | 2026-06-24 | Close | Closed | On Time
26 | Jun | NPI | Sample assembly Support | Injection sample JRI green digital sensor at harvard (T0) | JRI | Thiti | 2026-06-24 | 2026-06-24 | 2026-06-24 | Close | Closed | On Time
26 | Jun | MEETING | Meeting | Numworks weekly meeting | Numworks | Thiti | 2026-06-25 | 2026-06-25 | 2026-06-25 | Close | Closed | On Time
26 | Jun | DFA | Initial review custmer data for DFA | Confirm DFA Powerboard of viper version 14.5 |  | Bunnarak | 2026-06-24 | 2026-06-25 | 2026-06-25 | Close | Closed | On Time
26 | Jun | MEETING | Meeting | Kick-Off New Project AMW 03767 | Bernina | Bunnarak | 2026-06-24 | 2026-06-24 | 2026-06-24 | Close | Closed | On Time
26 | Jun | MEETING | Meeting | Kick off MCON Project | GUTOR | Bunnarak | 2026-06-25 | 2026-06-25 | 2026-06-25 | Close | Closed | On Time
26 | Jun | RFQ | RFQ | AMW QUO818 NPI Integrtaion requirement | GUTOR | Bunnarak | 2026-06-26 | 2026-06-29 | 2026-06-29 | Close | Closed | On Time
26 | Jun | PROJECT | KAIZEN | Prepare KAIZEN report |  | Bunnarak | 2026-06-26 | 2026-06-26 | 2026-06-29 | Close | Closed | Delay
26 | Jun | MEETING | Meeting | JRI weekly project review | JRI | Tae | 2026-06-22 | 2026-06-22 | 2026-06-22 | Close | Closed | On Time
26 | Jun | OTHER | Training | Basic Label Training by Brady |  | Tae | 2026-06-24 | 2026-06-24 | 2026-06-24 | Close | Closed | On Time
26 | Jun | MEETING | Meeting | Kick-Off New Project AMW 03767 | Bernina | Tae | 2026-06-24 | 2026-06-24 | 2026-06-24 | Close | Closed | On Time
26 | Jun | PROJECT | KAIZEN | Prepare KAIZEN report |  | Tae | 2026-06-24 | 2026-06-25 | 2026-06-25 | Close | Closed | On Time
26 | Jun | DFA | Initial review custmer data for DFA | Confirm DFA Powerboard of viper version 14.5 | EnerSys | Tae | 2026-06-24 | 2026-06-25 | 2026-06-25 | Close | Closed | On Time
26 | Jun | DFA | Initial review custmer data for DFA | Confirm 5 push pins – S08FNT0F Rev. H and 4 push pins – S08FNT0D Rev. J | EnerSys | Tae | 2026-06-24 | 2026-06-25 | 2026-06-25 | Close | Closed | On Time
26 | Jun | Part DFM | Initial review custmer data for DFM | Review Kick off MCON project | GUTOR | Tae | 2026-06-26 | 2026-06-30 | 2026-06-30 | Close | Closed | On Time
26 | Jun | RFQ | RFQ Packing | AMW-QUO972 Rev02.01 RFQ Packing | Gutor | Chutiporn | 2026-06-26 | 2026-06-29 | 2026-06-29 | Close | Closed | On Time
27 | Jun | PACKING | Support packing | AMW 03486-WE prepare and share packing concept | Fonroche | Chutiporn | 2026-06-29 | 2026-06-29 | 2026-06-29 | Close | Closed | On Time
27 | Jun | PACKING | Support packing | AMW 03734 prepare and share packing concept | Mattel | Chutiporn | 2026-06-29 | 2026-06-29 | 2026-06-29 | Close | Closed | On Time
27 | Jun | PACKING | Support packing | AMW 03743 STIWA prepare and share packing concept | Stiwa | Chutiporn | 2026-06-29 | 2026-06-29 | 2026-06-29 | Close | Closed | On Time
27 | Jun | RFQ | RFQ Packing | AMW QUO984 RFQ packing | Enersys | Chutiporn | 2026-06-29 | 2026-06-30 | 2026-06-29 | Close | Closed | On Time
27 | Jun | PACKING | Support packing | AMW 03502 prepare and share packing sample concept | Maatel | Chutiporn | 2026-06-29 | 2026-06-30 | 2026-06-29 | Close | Closed | On Time
27 | Jun | RFQ | RFQ Packing | AMW-QUO776 Rev03.01 RFQ Packing | Maatel | Chutiporn | 2026-06-30 | 2026-07-01 | 2026-06-30 | Close | Closed | On Time
27 | Jun | PACKING | Support packing | Prepare and sharing packing concept sample AMW03533SP, AMW03534SP, 03535 | Traco | Chutiporn | 2026-06-30 | 2026-07-01 | 2026-06-30 | Close | Closed | On Time
27 | Jun | PACKING | Design New Packaging | Update external pacckaging concept for mode AMW 03767 | Bernina | Chutiporn | 2026-06-30 | 2026-07-01 | 2026-07-01 | Close | Closed | On Time
27 | Jun | PACKING | Confirm packing | Confirm TRACO TIP MasterCarton packing concept | Traco | Chutiporn | 2026-06-30 | 2026-07-02 | 2026-07-02 | Close | Closed | On Time
27 | Jul | PACKING | Support packing | AMW 03719 prepare and sharing packing concept sample |  | Chutiporn | 2026-07-01 | 2026-07-01 | 2026-07-01 | Close | Closed | On Time
27 | Jul | RFQ | RFQ Packing | AMW 03617-00-01 Kit option packing standard | EnerSys | Chutiporn | 2026-07-02 | 2026-07-03 | 2026-07-02 | Close | Closed | On Time
27 | Jul | PACKING | Confirm packing | Confirm customer quetion for AMW03743 Haoticore4 | Stiwa | Chutiporn | 2026-07-03 | 2026-07-03 | 2026-07-03 | Close | Closed | On Time
27 | Jun | NPI | NPI Technical support | Preapare Action report for AMW 03676 LEACH that found packaging damaged | Leach | Thiti | 2026-06-29 | 2026-06-29 | 2026-06-29 | Close | Closed | On Time
27 | Jun | NPI | NPI Technical support | Review AMW 03668 overmolding's measurement data of HV and AMW | JRI | Thiti | 2026-06-29 | 2026-06-29 | 2026-06-29 | Close | Closed | On Time
27 | Jun | MEETING | Meeting | JRI Weekly meeting | JRI | Thiti | 2026-06-29 | 2026-06-29 | 2026-06-29 | Close | Closed | On Time
27 | Jun | NPI | NPI Technical support | Prepare improvement report for improvement Overmolding AMW 03668 to HV |  | Thiti | 2026-06-30 | 2026-06-30 | 2026-06-30 | Close | Closed | On Time
27 | Jun | NPI | NPI Technical support | Confirm JRI digital sensor product | JRI | Thiti | 2026-06-29 | 2026-06-30 | 2026-06-29 | Close | Closed | On Time
27 | Jun | NPI | NPI Technical support | Prepare cable spec for soldering of JRI AMW 03689 | JRI | Thiti | 2026-06-30 | 2026-07-02 | 2026-07-02 | Close | Closed | On Time
27 | Jul | MEETING | Meeting | Join meeting for ZWCAD software presentation |  | Thiti | 2026-07-01 | 2026-07-01 | 2026-07-01 | Close | Closed | On Time
27 | Jul | NPI | Trial tooling | Visit Satys for observe injection machine | JRI | Thiti | 2026-07-01 | 2026-07-01 | 2026-07-01 | Close | Closed | On Time
27 | Jul | NPI | NPI Technical support | Check 3D update for JRI AMW 03669 and prepare report for confim with customer | JRI | Thiti | 2026-07-01 | 2026-07-01 | 2026-07-01 | Close | Closed | On Time
27 | Jul | NPI | NPI Technical support | Confirm updated drawing of MAATEL AMW 03715 | Maatel | Thiti | 2026-07-01 | 2026-07-01 | 2026-07-01 | Close | Closed | On Time
27 | Jul | NPI | Checking part trial | Confirm plastic part plug nano T0 | JRI | Thiti | 2026-07-02 | 2026-07-02 | 2026-07-02 | Close | Closed | On Time
27 | Jul | NPI | NPI Technical support | Review DFM of MAATEL AMW 03715 after Cutomer feedback | Maatel | Thiti | 2026-07-03 | 2026-07-03 | 2026-07-03 | Close | Closed | On Time
27 | Jul | NPI | NPI Technical support | Prepare Jig concept for JRI AMW 03669&AMW 03670 |  | Thiti | 2026-07-03 | 2026-07-03 | 2026-07-03 | Close | Closed | On Time
27 | Jun | MEETING | Meeting | JRI Weekly meeting | JRI | Tae | 2026-06-29 | 2026-06-29 | 2026-06-29 | Close | Closed | On Time
27 | Jun | PACKING | Prepare customer label | Prepare label template for AMW 03767 | Bernina | Tae | 2026-06-29 | 2026-06-30 | 2026-06-29 | Close | Closed | On Time
27 | Jun | Part DFM | Initial review custmer data for DFM | Initial review DFM MCON | GUTOR | Tae | 2026-06-29 | 2026-07-01 | 2026-06-30 | Close | Closed | On Time
27 | Jun | DFA | Initial review custmer data for DFA | Initial review DFA MCON | GUTOR | Tae | 2026-06-29 | 2026-07-01 | 2026-06-30 | Close | Closed | On Time
27 | Jul | MEETING | Meeting | Join meeting for ZWCAD software presentation |  | Tae | 2026-07-01 | 2026-07-01 | 2026-07-01 | Close | Closed | On Time
27 | Jul | DFM Mold | DFM Feedback to Customer and waiting customer review | Confirm customer feed back AMW 03746 | JRI | Tae | 2026-07-01 | 2026-07-02 | 2026-07-02 | Close | Closed | On Time
27 | Jun | DFA | Initial review custmer data for DFA | Confirm item to request Eng to request Customer for DFM/DFA MCON project |  | Bunnarak | 2026-06-29 | 2026-06-29 | 2026-06-29 | Close | Closed | On Time
27 | Jun | PACKING | Design New Packaging | Create packing concept of magnetic follow customer request |  | Bunnarak | 2026-06-30 | 2026-07-02 | 2026-07-02 | Close | Closed | On Time
27 | Jul | NPI | Trial tooling | Visit Satys for observe injection machine | JRI | Bunnarak | 2026-07-01 | 2026-07-01 | 2026-07-01 | Close | Closed | On Time
27 | Jul | MEETING | Meeting | Join meeting for ZWCAD software presentation |  | Bunnarak | 2026-07-01 | 2026-07-01 | 2026-07-01 | Close | Closed | On Time
27 | Jul | PROJECT | KAIZEN | Prepare KAIZEN report |  | Bunnarak | 2026-07-02 | 2026-07-03 | 2026-07-03 | Close | Closed | On Time
28 | Jul | PACKING | Confirm packing | Confirm tray plug nano AMW03721 | JRI | Chutiporn | 2026-07-06 | 2026-07-07 | 2026-07-06 | Close | Closed | On Time
28 | Jul | PACKING | Design New Packaging | AMW 03542 prepare temp packing concept |  | Chutiporn | 2026-07-06 | 2026-07-07 | 2026-07-06 | Close | Closed | On Time
28 | Jul | PACKING | Design New Packaging | AMW 03685 prepare temp packing concept |  | Chutiporn | 2026-07-06 | 2026-07-07 | 2026-07-06 | Close | Closed | On Time
28 | Jul | PACKING | Confirm packing | Confirm Packing standard for external send of AMW 03754, AMW03755 |  | Chutiporn | 2026-07-07 | 2026-07-08 | 2026-07-08 | Close | Closed | On Time
28 | Jul | PACKING | Confirm packing | Confirm tray plug nano AMW03721 Rev2 | JRI | Chutiporn | 2026-07-07 | 2026-07-08 | 2026-07-08 | Close | Closed | On Time
28 | Jul | PACKING | Confirm packing | Confirm tray of bernina AMW 03767 | Bernina | Chutiporn | 2026-07-09 | 2026-07-10 | 2026-07-09 | Close | Closed | On Time
28 | Jul | PACKING | Design New Packaging | AMW 03661 share temp pack concept |  | Chutiporn | 2026-07-09 | 2026-07-10 | 2026-07-09 | Close | Closed | On Time
28 | Jul | RFQ | RFQ Packing | AMW QUO981 RFQ packing | Traco | Chutiporn | 2026-07-09 | 2026-07-10 |  | On process | On time
28 | Jul | RFQ | RFQ Packing | AMW QUO818 rev 03.01 RFQ packaging | GUTOR | Chutiporn | 2026-07-09 | 2026-07-10 |  | On process | On time
28 | Jul | RFQ | RFQ Packing | AMW QUO997 RFQ Packing | Molex | Chutiporn | 2026-07-09 | 2026-07-10 | 2026-07-09 | Close | Closed | On Time
28 | Jul | PACKING | Confirm packing | Technical support trial individual box for numworks SP | Numworks | Chutiporn | 2026-07-10 | 2026-07-10 |  | On process | On time
28 | Jul | PACKING | Prepare customer label | Update label template of AMW 03486-WE |  | Tae | 2026-07-06 | 2026-07-06 | 2026-07-06 | Close | Closed | On Time
28 | Jul | MEETING | Meeting | JRI Weekly meeting | JRI | Tae | 2026-07-06 | 2026-07-06 | 2026-07-06 | Close | Closed | On Time
28 | Jul | Part DFM | Initial review custmer data for DFM | Part DFM MCON | Gutor | Tae | 2026-07-06 | 2026-07-08 | 2026-07-08 | Close | Closed | On Time
28 | Jul | DFA | Review internal DFA | DFA MCON | Gutor | Tae | 2026-07-06 | 2026-07-08 | 2026-07-08 | Close | Closed | On Time
28 | Jul | NPI | NPI Technical support | Weekly tooling progress follow up(AMW-YPC) Stand-alone project | Enersys | Tae | 2026-07-07 | 2026-07-07 | 2026-07-07 | Close | Closed | On Time
28 | Jul | PACKING | Prepare customer label | Update label template of Gutor IGBT ANW 03256-R.BD | GUTOR | Tae | 2026-07-07 | 2026-07-08 | 2026-07-08 | Close | Closed | On Time
28 | Jul | NPI | Checking part trial | Confirm assembly plug nano T0 Metal with plastic part | JRI | Tae | 2026-07-08 | 2026-07-09 | 2026-07-09 | Close | Closed | On Time
28 | Jul | DFA | Initial review custmer data for DFA | Review DFA for light guide and CoverPanel of Cabinet viper | Enersys | Tae | 2026-07-08 | 2026-07-09 | 2026-07-08 | Close | Closed | On Time
28 | Jul | PROJECT | KAIZEN | Confirm foam Estimate Quotation for Kaizen | Gutor | Tae | 2026-07-10 | 2026-07-10 |  | On process | On time
28 | Jul | MEETING | Meeting | JRI Weekly meeting | JRI | Thiti | 2026-07-06 | 2026-07-06 | 2026-07-06 | Close | Closed | On Time
28 | Jul | MEETING | Meeting | JRI Overmold project meeting | JRI | Thiti | 2026-07-06 | 2026-07-06 | 2026-07-06 | Close | Closed | On Time
28 | Jul | NPI | NPI Technical support | Weekly tooling progress follow up(AMW-YPC) Stand-alone project | Enersys | Thiti | 2026-07-07 | 2026-07-07 | 2026-07-07 | Close | Closed | On Time
28 | Jul | NPI | NPI Technical support | Weekly tooling progress follow up(AMW-YPC) Stand-alone project | Enersys | Thiti | 2026-07-07 | 2026-07-07 | 2026-07-07 | Close | Closed | On Time
28 | Jul | DFM Mold | Review DFM MOLD and feed back | AMW-QUO770 Rev 01.01 _ Project IM65XI DFM Mold | Maatel | Thiti | 2026-07-08 | 2026-07-09 | 2026-07-09 | Close | Closed | On Time
28 | Jul | MEETING | Meeting | Numworks weekly meeting | Numworks | Thiti | 2026-07-09 | 2026-07-09 | 2026-07-09 | Close | Closed | On Time
28 | Jul | NPI | NPI Technical support | AMW 03669/AMW 03670 3D confirmation. | JRI | Thiti | 2026-07-09 | 2026-07-09 | 2026-07-09 | Close | Closed | On Time
28 | Jul | NPI | NPI Technical support | Overmold project follow up specification and document with satys | JRI | Thiti | 2026-07-09 | 2026-07-14 |  | On process | On time
28 | Jul | RFQ | RFQ | AMW QUO981 NPI integration requirement | Traco | Bunnarak | 2026-07-07 | 2026-07-08 | 2026-07-07 | Close | Closed | On Time
28 | Jul | Part DFM | Review internal DFM | Check DFM/DFA MCON | Gutor | Bunnarak | 2026-07-07 | 2026-07-08 | 2026-07-07 | Close | Closed | On Time
28 | Jul | PROJECT | KAIZEN | Create kaizen ducument |  | Bunnarak | 2026-07-07 | 2026-07-09 | 2026-07-09 | Close | Closed | On Time
28 | Jul | PACKING | Design New Packaging | Update pallet layout for Numworks | Numworks | Bunnarak | 2026-07-08 | 2026-07-10 |  | On process | On time
Formulas:
WW = WEEKNUM(Table6[[#This Row],[Start Date]])
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Refer
| Category | Column1
Sort | Category | Task name | Name List | Category | Sort | Category
1 | NPI | Sample assembly Support | Bunnarak | RFQ | 1 | NPI | Niran
1 | NPI | Pilot assembly Support | Tae | NPI | 2 | DFM Mold | Tanawit | ข
1 | NPI | PreSerise assembly Support | Thiti | DFM | 3 | Part DFM | Somchai
1 | NPI | Trial tooling | Nattachai | OTHER | 4 | RFQ | Vanassanan
1 | NPI | Quality Issue Analysis | Chutiporn | Internal DFM | 5 | PROJECT | All
1 | NPI | NPI Technical support | All | PROJECT | 6 | MEETING
1 | NPI | Review OPL |  | MEETING | 7 | OTHER
1 | NPI | Review JIG concept |  | DFA | 8 | DFA
1 | NPI | Create drawing |  |  | 9 | PACKING
9 | PACKING | Design New Packaging
9 | PACKING | Support packing
2 | DFM Mold | Review DFM Part Drawing and feed back
2 | DFM Mold | Review DFM MOLD and feed back
2 | DFM Mold | DFM Feedback to Customer and waiting customer review
2 | DFM Mold | Review Revised Data and Final DFM Mold Approval
3 | Part DFM | Initial review custmer data for DFM
3 | Part DFM | Review internal DFM
3 | Part DFM | Review Revised Data and Final internal DFM Approval
3 | Part DFM | Review Part and Assembly level
3 | Part DFM | Confirm Q'ty for assembly event and time to assembly
4 | RFQ | RFQ
4 | RFQ | RFQ Packing
5 | PROJECT | KAIZEN
9 | PACKING | Prepare customer label
9 | PACKING | Confirm packing
5 | PROJECT | Improve working process
1 | NPI | MP assembly support
1 | NPI | Checking part trial
6 | MEETING | Meeting
7 | OTHER | Training
7 | OTHER | Support register document
7 | OTHER | Process Improvement
7 | OTHER | Create standard document
7 | OTHER | Planing
7 | OTHER | Interview candidate new member
7 | OTHER | 5S meeting
7 | OTHER | Visit Exhibition
8 | DFA | Initial review custmer data for DFA
8 | DFA | Create assembly flow
8 | DFA | Review internal DFA
8 | DFA | DFA Feedback to Customer and waiting customer review
8 | DFA | Review Revised Data and Final internal DFA Approval
7 | OTHER | Support adjust CAD data

## Pivot monthly
Ratio |  |  | Pending task | [12 empty] | Close vs open | [5 empty] | Overdue | [10 empty] | Status | Close
[29 empty] | OverDue Aleart | (หลายรายการ)
| ป้ายชื่อแถว | Count of TASK |  | Count of Status | ป้ายชื่อคอลัมน์ | [6 empty] | sort |  |  |  |  | Count of Status |  | ป้ายชื่อคอลัมน์ |  |  |  | Count of OverDue Aleart |  | ป้ายชื่อคอลัมน์ | [7 empty] | Count of Performace status |  | ป้ายชื่อคอลัมน์ |  | total | 659
| NPI | 187 |  | ป้ายชื่อแถว | Close | On process |  | Type | Close | On process |  | Type | Close | On Process |  |  | ป้ายชื่อแถว | WW | Close | On process | (ว่าง) |  | ป้ายชื่อแถว | WW | Overdue | Closed | On time | (ว่าง) | ป้ายชื่อแถว | Type | TASK | Target Date | ป้ายชื่อแถว | WW | On Time | ผลรวมทั้งหมด | ontime | 659 | 100%
| MEETING | 75 |  | MEETING | 75 |  |  | RFQ | 65 | 2 |  | RFQ | 65 | 2 |  |  | May | 19 | 14 |  |  |  | May |  |  | 109 | [6 empty] | May |  | 109 | 109 | delay | 0 | 0%
| OTHER | 31 |  | NPI | 186 | 1 |  | NPI | 186 | 1 |  | NPI | 186 | 1 |  |  | May | 20 | 28 |  |  |  | Jun |  |  | 133 | [6 empty] | Jun |  | 132 | 132
| DFA | 20 |  | OTHER | 31 |  |  | DFM | 0 | 0 |  | PROJECT | 6 | 1 |  |  | May | 21 | 39 |  |  |  | Jul | 27 |  | 15 | [6 empty] | Jul | 27 | 15 | 15
| PROJECT | 7 |  | DFA | 20 |  |  | OTHER | 31 | 0 |  | DFM | 0 | 0 |  |  | May | 22 | 28 |  |  |  | Jul | 28 |  | 26 | 6 | [5 empty] | Jul | 28 | 26 | 26
| RFQ | 67 |  | PROJECT | 6 | 1 |  | Internal DFM | 0 | 0 |  | OTHER | 31 | 0 |  |  | Jun | 24 | 35 |  |  |  | Jan | 2 |  | 20 | [6 empty] | Jan | 2 | 20 | 20
|  |  |  | RFQ | 65 | 2 |  | PROJECT | 6 | 1 |  | Internal DFM | 0 | 0 |  |  | Jun | 25 | 30 |  |  |  | Jan | 3 |  | 22 | [6 empty] | Jan | 3 | 22 | 22
| PACKING | 199 |  |  | 1 |  |  | MEETING | 75 | 0 |  | MEETING | 75 | 0 |  |  | Jun | 26 | 24 |  |  |  | Jan | 4 |  | 26 | [6 empty] | Jan | 4 | 26 | 26
| Part DFM | 15 |  | PACKING | 197 | 2 |  | DFA | 20 | 0 |  | DFA | 20 | 0 |  |  | Jun | 27 | 21 |  |  |  | Jan | 5 |  | 27 | [6 empty] | Jan | 5 | 27 | 27
other task | DFM Mold | 64 | Weekly ratio | Part DFM | 15 |  |  | PACKING | 197 | 2 |  | PACKING | 197 | 2 |  |  | Jun | 23 | 23 |  |  |  | Feb | 7 |  | 25 | [6 empty] | Feb | 7 | 25 | 25
|  |  |  | DFM Mold | 64 | [11 empty] | Jul | 27 | 15 |  |  |  | Feb | 8 |  | 26 | [6 empty] | Feb | 8 | 26 | 26
| Type | RFQ |  | Count of TASK |  | ป้ายชื่อคอลัมน์ | [10 empty] | Jul | 28 | 26 | 6 |  |  | Feb | 6 |  | 17 | [6 empty] | Feb | 6 | 17 | 17
|  |  |  | ป้ายชื่อแถว | WW | NPI | MEETING | OTHER | DFA | PROJECT | RFQ |  | PACKING | Part DFM | DFM Mold |  | Jan | 2 | 20 |  |  |  | Feb | 9 |  | 29 | [6 empty] | Feb | 9 | 29 | 29
| ป้ายชื่อแถว | Count of TASK |  | May |  | 4 | 6 | 1 |  | 1 | 9 |  | 46 | 3 | 39 |  | Jan | 3 | 22 |  |  |  | Mar | 10 |  | 21 | [6 empty] | Mar | 10 | 21 | 21
| RFQ | 10 |  | Jun |  | 20 | 19 | 5 | 8 | 3 | 12 |  | 52 | 4 | 9 |  | Jan | 4 | 26 |  |  |  | Mar | 13 |  | 25 | [6 empty] | Mar | 13 | 25 | 25
| RFQ Packing | 57 |  | Jul | 27 | 7 | 3 |  |  | 1 | 1 |  | 2 |  | 1 |  | Jan | 5 | 27 |  |  |  | Mar | 11 |  | 36 | [6 empty] | Mar | 11 | 36 | 36
|  |  |  | Jul | 28 | 6 | 4 |  | 2 | 2 | 4 |  | 11 | 2 | 1 |  | Feb | 7 | 25 |  |  |  | Mar | 12 |  | 34 | [6 empty] | Mar | 12 | 34 | 34
|  |  |  | Jan | 2 | 10 | 3 | 1 |  |  | 1 |  | 5 |  |  |  | Feb | 8 | 26 |  |  |  | Mar | 14 |  | 10 | [6 empty] | Mar | 14 | 10 | 10
|  |  |  | Jan | 3 | 10 | 2 | 3 |  |  | 3 |  | 3 | 1 |  |  | Feb | 6 | 17 |  |  |  | Apr | 17 |  | 21 | [6 empty] | Apr | 17 | 21 | 21
|  |  |  | Jan | 4 | 4 | 1 | 1 | 5 |  | 1 |  | 9 | 4 | 1 |  | Feb | 9 | 29 |  |  |  | Apr | 14 |  | 11 | [6 empty] | Apr | 14 | 11 | 11
|  |  |  | Jan | 5 | 11 | 3 | 1 | 1 |  | 1 |  | 5 |  | 5 |  | Mar | 10 | 21 |  |  |  | Apr | 15 |  | 12 | [6 empty] | Apr | 15 | 12 | 12
|  |  |  | Feb | 7 | 8 | 2 | 1 | 1 |  | 7 |  | 5 |  | 1 |  | Mar | 13 | 25 |  |  |  | Apr | 18 |  | 15 | [6 empty] | Apr | 18 | 15 | 15
|  |  |  | Feb | 8 | 7 | 4 | 3 | 1 |  | 2 |  | 7 |  | 2 |  | Mar | 11 | 36 | [13 empty] | ผลรวมทั้งหมด |  | 659 | 659
|  |  |  | Feb | 6 | 5 | 2 | 2 |  |  | 2 |  | 5 |  | 1 |  | Mar | 12 | 34
|  |  |  | Feb | 9 | 19 | 1 | 1 |  |  | 2 |  | 6 |  |  |  | Mar | 14 | 10
|  |  |  | Mar | 10 | 8 | 1 | 7 |  |  | 4 |  | 1 |  |  |  | Apr | 17 | 21
|  |  |  | Mar | 13 | 15 | 2 | 1 |  |  | 2 |  | 5 |  |  |  | Apr | 14 | 11
|  |  |  | Mar | 11 | 12 | 9 | 2 |  |  | 3 |  | 10 |  |  |  | Apr | 15 | 12
|  |  |  | Mar | 12 | 22 | 2 |  | 1 |  | 2 |  | 3 |  | 4 |  | Apr | 18 | 15
|  |  |  | Mar | 14 | 3 | 3 |  |  |  | 3 |  | 1
|  |  |  | Apr | 17 | 5 | 1 | 2 |  |  | 2 |  | 10 | 1
|  |  |  | Apr | 14 | 7 | 1 |  |  |  | 1 |  | 2
|  |  |  | Apr | 15 | 3 | 6 | [5 empty] | 3
|  |  |  | Apr | 18 | 1 |  |  | 1 |  | 5 |  | 8

## Pivot
Ratio |  |  | Pending task | [12 empty] | Close vs open | [5 empty] | Overdue | [10 empty] | Status | Close
[29 empty] | OverDue Aleart | (หลายรายการ)
| ป้ายชื่อแถว | Count of TASK |  | Count of Status | ป้ายชื่อคอลัมน์ | [6 empty] | sort |  |  |  |  | Count of Status |  | ป้ายชื่อคอลัมน์ |  |  |  | Count of OverDue Aleart |  | ป้ายชื่อคอลัมน์ | [7 empty] | Count of Performace status |  | ป้ายชื่อคอลัมน์ |  | total | 659
| NPI | 187 |  | ป้ายชื่อแถว | Close | On process |  | Type | Close | On process |  | Type | Close | On Process |  |  | ป้ายชื่อแถว | WW | Close | On process | (ว่าง) |  | ป้ายชื่อแถว | WW | Overdue | Closed | On time | (ว่าง) | ป้ายชื่อแถว | Type | TASK | Target Date | ป้ายชื่อแถว | WW | On Time | ผลรวมทั้งหมด | ontime | 659 | 100%
| DFM Mold | 64 |  | DFM Mold | 64 |  |  | RFQ | 65 | 2 |  | RFQ | 65 | 2 |  |  | May | 19 | 14 |  |  |  | May | 19 |  | 14 | [6 empty] | May | 19 | 14 | 14 | delay | 0 | 0%
| Part DFM | 15 |  | MEETING | 75 |  |  | NPI | 186 | 1 |  | NPI | 186 | 1 |  |  | May | 20 | 28 |  |  |  | May | 20 |  | 28 | [6 empty] | May | 20 | 28 | 28
| MEETING | 75 |  | NPI | 186 | 1 |  | DFM Mold | 64 | 0 |  | PROJECT | 6 | 1 |  |  | May | 21 | 39 |  |  |  | May | 21 |  | 39 | [6 empty] | May | 21 | 39 | 39
| OTHER | 31 |  | OTHER | 31 |  |  | OTHER | 31 | 0 |  | DFM Mold | 64 | 0 |  |  | May | 22 | 28 |  |  |  | May | 22 |  | 28 | [6 empty] | May | 22 | 28 | 28
| DFA | 20 |  | DFA | 20 |  |  | Part DFM | 0 | 0 |  | OTHER | 31 | 0 |  |  | Jun | 24 | 35 |  |  |  | Jun | 24 |  | 35 | [6 empty] | Jun | 24 | 35 | 35
| PROJECT | 7 |  | PROJECT | 6 | 1 |  | PROJECT | 6 | 1 |  | Part DFM | 0 | 0 |  |  | Jun | 25 | 30 |  |  |  | Jun | 25 |  | 30 | [6 empty] | Jun | 25 | 30 | 30
| RFQ | 67 |  | RFQ | 65 | 2 |  | MEETING | 75 | 0 |  | MEETING | 75 | 0 |  |  | Jun | 26 | 24 |  |  |  | Jun | 26 |  | 24 | [6 empty] | Jun | 26 | 23 | 23
| PACKING | 199 |  | PACKING | 197 | 2 |  | DFA | 20 | 0 |  | DFA | 20 | 0 |  |  | Jun | 27 | 21 |  |  |  | Jun | 27 |  | 21 | [6 empty] | Jun | 27 | 21 | 21
other task |  |  | Weekly ratio |  |  |  |  | PACKING | 197 | 2 |  | PACKING | 197 | 2 |  |  | Jun | 23 | 23 |  |  |  | Jun | 23 |  | 23 | [6 empty] | Jun | 23 | 23 | 23
[17 empty] | Jul | 27 | 15 |  |  |  | Jul | 27 |  | 15 | [6 empty] | Jul | 27 | 15 | 15
| Type | OTHER |  | Count of TASK |  | ป้ายชื่อคอลัมน์ | [10 empty] | Jul | 28 | 26 | 6 |  |  | Jul | 28 |  | 26 | 6 | [5 empty] | Jul | 28 | 26 | 26
|  |  |  | ป้ายชื่อแถว | WW | NPI | MEETING | OTHER | DFA | PROJECT | RFQ |  | PACKING | Part DFM | DFM Mold |  | Jan | 2 | 20 |  |  |  | Jan | 2 |  | 20 | [6 empty] | Jan | 2 | 20 | 20
| ป้ายชื่อแถว | Count of TASK |  | May | 19 | [5 empty] | 3 |  | 10 |  | 1 |  | Jan | 3 | 22 |  |  |  | Jan | 3 |  | 22 | [6 empty] | Jan | 3 | 22 | 22
| Create standard document | 2 |  | May | 20 |  | 1 |  |  |  | 2 |  | 2 |  | 23 |  | Jan | 4 | 26 |  |  |  | Jan | 4 |  | 26 | [6 empty] | Jan | 4 | 26 | 26
| Training | 20 |  | May | 21 | 2 | 3 |  |  | 1 | 2 |  | 22 |  | 9 |  | Jan | 5 | 27 |  |  |  | Jan | 5 |  | 27 | [6 empty] | Jan | 5 | 27 | 27
| Interview candidate new member | 1 |  | May | 22 | 2 | 2 | 1 |  |  | 2 |  | 12 | 3 | 6 |  | Feb | 7 | 25 |  |  |  | Feb | 7 |  | 25 | [6 empty] | Feb | 7 | 25 | 25
| 5S meeting | 2 |  | Jun | 24 | 5 | 2 | 1 |  |  | 2 |  | 18 | 1 | 6 |  | Feb | 8 | 26 |  |  |  | Feb | 8 |  | 26 | [6 empty] | Feb | 8 | 26 | 26
| Support register document | 1 |  | Jun | 25 | 5 | 5 | 3 | 1 | 1 | 2 |  | 10 | 1 | 2 |  | Feb | 6 | 17 |  |  |  | Feb | 6 |  | 17 | [6 empty] | Feb | 6 | 17 | 17
| Visit Exhibition | 5 |  | Jun | 26 | 1 | 8 | 1 | 3 | 2 | 3 |  | 4 | 1 |  |  | Feb | 9 | 29 |  |  |  | Feb | 9 |  | 29 | [6 empty] | Feb | 9 | 29 | 29
|  |  |  | Jun | 27 | 5 | 2 |  | 2 |  | 2 |  | 9 | 1 |  |  | Mar | 10 | 21 |  |  |  | Mar | 10 |  | 21 | [6 empty] | Mar | 10 | 21 | 21
|  |  |  | Jun | 23 | 4 | 2 |  | 2 |  | 3 |  | 11 |  | 1 |  | Mar | 13 | 25 |  |  |  | Mar | 13 |  | 25 | [6 empty] | Mar | 13 | 25 | 25
|  |  |  | Jul | 27 | 7 | 3 |  |  | 1 | 1 |  | 2 |  | 1 |  | Mar | 11 | 36 |  |  |  | Mar | 11 |  | 36 | [6 empty] | Mar | 11 | 36 | 36
|  |  |  | Jul | 28 | 6 | 4 |  | 2 | 2 | 4 |  | 11 | 2 | 1 |  | Mar | 12 | 34 |  |  |  | Mar | 12 |  | 34 | [6 empty] | Mar | 12 | 34 | 34
|  |  |  | Jan | 2 | 10 | 3 | 1 |  |  | 1 |  | 5 |  |  |  | Mar | 14 | 10 |  |  |  | Mar | 14 |  | 10 | [6 empty] | Mar | 14 | 10 | 10
|  |  |  | Jan | 3 | 10 | 2 | 3 |  |  | 3 |  | 3 | 1 |  |  | Apr | 17 | 21 |  |  |  | Apr | 17 |  | 21 | [6 empty] | Apr | 17 | 21 | 21
|  |  |  | Jan | 4 | 4 | 1 | 1 | 5 |  | 1 |  | 9 | 4 | 1 |  | Apr | 14 | 11 |  |  |  | Apr | 14 |  | 11 | [6 empty] | Apr | 14 | 11 | 11
|  |  |  | Jan | 5 | 11 | 3 | 1 | 1 |  | 1 |  | 5 |  | 5 |  | Apr | 15 | 12 |  |  |  | Apr | 15 |  | 12 | [6 empty] | Apr | 15 | 12 | 12
|  |  |  | Feb | 7 | 8 | 2 | 1 | 1 |  | 7 |  | 5 |  | 1 |  | Apr | 18 | 15 |  |  |  | Apr | 18 |  | 15 | [6 empty] | Apr | 18 | 15 | 15
|  |  |  | Feb | 8 | 7 | 4 | 3 | 1 |  | 2 |  | 7 |  | 2 | [17 empty] | ผลรวมทั้งหมด |  | 659 | 659
|  |  |  | Feb | 6 | 5 | 2 | 2 |  |  | 2 |  | 5 |  | 1
| ป้ายชื่อแถว |  |  | Feb | 9 | 19 | 1 | 1 |  |  | 2 |  | 6
| All |  |  | Mar | 10 | 8 | 1 | 7 |  |  | 4 |  | 1
| Bunnarak |  |  | Mar | 13 | 15 | 2 | 1 |  |  | 2 |  | 5
| Thiti |  |  | Mar | 11 | 12 | 9 | 2 |  |  | 3 |  | 10
| Nattachai |  |  | Mar | 12 | 22 | 2 |  | 1 |  | 2 |  | 3 |  | 4
| Chutiporn |  |  | Mar | 14 | 3 | 3 |  |  |  | 3 |  | 1
| Tae |  |  | Apr | 17 | 5 | 1 | 2 |  |  | 2 |  | 10 | 1
| ผลรวมทั้งหมด |  |  | Apr | 14 | 7 | 1 |  |  |  | 1 |  | 2
|  |  |  | Apr | 15 | 3 | 6 | [5 empty] | 3
|  |  |  | Apr | 18 | 1 |  |  | 1 |  | 5 |  | 8

## Progress report
PIC | Task count |  | Customer | Task count
Bunnarak | 133 |  | Cat Power Design | 0
Tae | 75 |  | AEG | 14
All | 2 |  | Atlantic | 3
Chutiporn | 81 |  | Blue Wave Technologies | 0
Thiti | 220 |  | Enersys | 128
Tea | 0 |  | Fairland | 6
| 511 |  | IES | 22
|  |  | JRI | 102
|  |  | Leach | 13
|  |  | Maatel | 19
|  |  | Numworks | 126
|  |  | FONROCHE | 30
Fonroche